## Instructions
Severity | Description
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
Points in Iteration | Action
Points < 10 | Use the planned debugging time in the iteration.
Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.

## Bug Metrics
Bug Metrics
S/N | Iteration | Function | Description | Severity | Points | Final Bug Metric (Points Total) | Mitgation
1 | 1 | Login (Student) | Successful login brought the user to 'Plan Bid' page instead of the student home page | High | 5 | 26 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
2 | 1 | Login (Student) | User name displayed on home page did not change according to the user that logged in | Low | 1
3 | 1 | Login (Admin) | Admin got directed to student home page instead of bidding admin page and hence causing error and causes login to be unsuccessful | High | 5
4 | 1 | Login (Admin) | Admin is able to login successfully when they key in their password in caps | High | 5
5 | 1 | Login (Student) | Student is able to login successfully when they select their role as admin and was brought to the bidding admin page | Critical | 10
6 | 2 | Bootstrap | Cannot truncate a table referenced in a foreign key constraint (`is212_spm_data`.`bid`, CONSTRAINT `bid_fk1` FOREIGN KEY (`userid`) | Critical | 10
7 | 2 | Bootstrap | Incorrect variable name | Critical | 10
8 | 2 | Bootstrap | Error due to calling class methods inside a PDO function | Critical | 10
9 | 2 | Bootstrap | Too few arguments in 'validateDate()' | Critical | 10
10 | 2 | Bootstrap | Column not found: Unknown column 'round_number' in line 32 of RoundDAO.php | Critical | 10
11 | 2 | Bootstrap | Issue with the validateDate() function in common.php, causing all course rows to be ignored | High | 5
12 | 2 | Bootstrap | Incorrect row numbers shown in bootstrap errors | Low | 1
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198

## Bug Log
Bug Log
S/N | Iteration | Function | Description | Status | Discovered On | Resolved On | Fixed by (PP Team)
1 | 1 | Login (Student) | Successful login brought the user to 'Plan Bid' page instead of the student home page | Resolved | 2017-10-01 | 2017-10-01 | J & K
2 | 1 | Login (Student) | User name displayed on home page did not change according to the user that logged in | Resolved | 2017-10-01 | 2017-10-01 | J & K
3 | #REF! | #REF! | #REF! | Resolved | 2017-10-01 | 2017-10-01 | J & K
4 | #REF! | #REF! | #REF! | Unresolved | 2017-10-01
5 | #REF! | #REF! | #REF! | Resolved | 2017-10-01 | 2017-10-01 | J & K
6 | #REF! | #REF! | #REF! | Resolved | 2017-10-01 | 2017-10-04 | H & W
7 | #REF! | #REF! | #REF! | Resolved | 2017-10-04 | 2017-10-05 | H & W
8 | #REF! | #REF! | #REF! | Resolved | 2017-10-05 | 13/10/2017 | H & W
9 | 4 | Bootstrap | #REF! | Resolved | 22/10/2017 | 22/10/2017 | H & W
9 | 3 | Heatmap | #REF! | Resolved | 13/10/2017 | 13/10/2017 | W & P
10 | 3 | Heatmap | #REF! | Resolved | 13/10/2017 | 13/10/2017 | W & P
11 | 3 | Heatmap | #REF! | Resolved | 13/10/2017 | 13/10/2017 | W & P
13 | 3 | Heatmap | #REF! | Resolved | 14/10/2017 | 14/10/2017 | H & J
14 | 4 | Popular Place | #REF! | Resolved | 22/10/2017 | 22/10/2017 | H & J
15 | 4 | Popular Place | #REF! | Resolved | 22/10/2017 | 22/10/2017 | H & K
16 | 4 | Popular Place | #REF! | Resolved | 22/10/2017 | 22/10/2017 | H & K
17 | #REF! | #REF! | #REF! | Unresolved | 22/10/2017
18 | #REF! | #REF! | #REF! | Unresolved | 22/10/2017
19 | #REF! | #REF! | #REF! | Resolved | 2017-10-21 | 2017-10-21 | J & P
20 | #REF! | #REF! | #REF! | Resolved | 2017-10-21 | 2017-10-21 | J & P
21 | #REF! | #REF! | #REF! | Resolved | 2017-10-21 | 2017-10-21 | J & P