## Instructions
Severity | Description
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
Points in Iteration | Action
Points < 10 | Use the planned debugging time in the iteration.
Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.

## Bug Metrics
Bug Metrics
S/N | Iteration | Function | Description | Severity | Points | Final Bug Metric (Points Total) | Mitgation
1 | 1 | Login (Student) | Successful login brought the user to 'Plan Bid' page instead of the student home page | High | 5 | 26 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
2 | 1 | Login (Student) | User name displayed on home page did not change according to the user that logged in | Low | 1
3 | 1 | Login (Admin) | Admin got directed to student home page instead of bidding admin page and hence causing error and causes login to be unsuccessful | High | 5
4 | 1 | Login (Admin) | Admin is able to login successfully when they key in their password in caps | High | 5
5 | 1 | Login (Student) | Student is able to login successfully when they select their role as admin and was brought to the bidding admin page | Critical | 10
6 | 2 | Add Bid | Your bid was placed successfully!' was displayed instead of the expected error message when student enters non-existing course code | High | 5 | 156 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
7 | 2 | Add Bid | Student was able to bid for course that are not offered by their school during round 1 | High | 5
8 | 2 | Add Bid | Student was able to bid for courses where they have not fulfilled the necessary pre-requisite course(s) | High | 5
9 | 2 | Bootstrap | SQL error: Tables could not be truncated due to foreign key constraints | Critical | 10
10 | 2 | Bootstrap | Incorrect variable name | Critical | 10
11 | 2 | Bootstrap | Error due to calling class methods inside a PDO function | Critical | 10
12 | 2 | Bootstrap | Too few arguments in 'validateDate()' | Critical | 10
13 | 2 | Bootstrap | SQL error: Column not found (used wrong column name) | Critical | 10
14 | 2 | Bootstrap | Issue with the validateDate() function in common.php, causing all exam dates to be invalid | High | 5
15 | 2 | Bootstrap | Incorrect row numbers shown in bootstrap errors | Low | 1
16 | 2 | Drop Bid | Cannot access private property Student::$edollar | High | 5
17 | 2 | Drop Bid | After dropping bid, updated e$ amount is not displayed | Low | 1
18 | 2 | Bootstrap | Undefined variable: getCourse | Critical | 10
19 | 2 | Bootstrap | Call to undefined method Prerequisite::getUserid() in CourseCompletedDAO.php | Critical | 10
20 | 2 | Bootstrap | Too few arguments for function $sectionDAO->retrieve() on line 538 | Critical | 10
21 | 2 | Bootstrap | Undefined variable: alreadyBidded | Critical | 10
22 | 2 | Bootstrap | SQL error: Failed to update due to the use of wrong variable name | Critical | 10
23 | 2 | Bootstrap | SQL error: duplicate entry due to incorrect validations against bid for same section | Critical | 10
24 | 2 | Bootstrap | Edollar balance not updated in database | High | 5
25 | 2 | Bootstrap | Edollar balance not updated in database | High | 5
26 | 2 | Bootstrap | Bootstrap succesful but error are not reported when the pre-requisite course has yet to be attempted | Low | 1
27 | 2 | Bootstrap | Bootstrap successful but error not displayed when amount in bidded is less than e$10 | Low | 1
28 | 2 | Bootstrap | Bootstrap unsuccessful and bid has entered the database when the amount in bid is less than e$10 | High | 5
29 | 2 | Bootstrap | No error displayed for when student is unable to place bids when there is insufficient e$ | Low | 1
30 | 2 | Bootstrap | Bootstrap unsuccessful due to incorrect data input in the bootstrap folder | Low | 1
31 | 3 | JSON Authenticate | Entered correct admin credentials, but was shown 'error: userid cannot be empty' | High | 5 | 142 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
32 | 3 | JSON Authenticate | Incorrect error messages displayed | Low | 1
33 | 3 | JSON Start | Redirected to login.php | Critical | 10
34 | 3 | JSON Start | Round 2 was started when round 1 was already started | High | 5
35 | 3 | JSON Stop | Invalid offset in processBids() function | Critical | 10
36 | 3 | JSON Stop | Undefined variable: UpdateStatusOK | Critical | 10
37 | 3 | JSON Update Bid | API was taking in POST parameters instead of GET | Critical | 10
38 | 3 | JSON Update Bid | Only one error message displayed when many were expected | High | 5
39 | 3 | JSON Update Bid | Error displayed due to existing bid when the existing bid should be updated | High | 5
40 | 3 | JSON Update Bid | array_values() expects parameter 1 to be array, boolean given on line number 2 | Critical | 10
41 | 3 | JSON Delete Bid | Only one error message displayed when many were expected (wrong syntax for appending error messages to array) | High | 5
42 | 3 | JSON Delete Bid | Undefined variable: student | Critical | 10
43 | 3 | JSON Delete Bid | Undefined variable: biddedamount | Critical | 10
44 | 3 | JSON Delete Bid | Section could be dropped when only pending bids should be dropped | High | 5
45 | 3 | JSON Delete Section | Only one error message displayed when many were expected | High | 5
46 | 3 | JSON Dump Bid | Entered valid inputs, but was given 'error' with 'null' messages | High | 5
47 | 3 | JSON Dump Section | Wrong error message for common validations | Low | 1
48 | 3 | Round2 logic clearing | Bidding results not displayed when round 2 is closed | Critical | 10
49 | 3 | Round2 logic clearing | Unable to drop section (from successful bid in round 1) when round 2 is open | Critical | 10
50 | 3 | Round2 logic clearing | Placing bid is successful when the exam timetable clash | High | 5
51 | 3 | Round2 logic clearing | Able to place bids for same course and section already bidded succesfully in round 1 (status: Success) regardless of vacancy | High | 5
52 | 4 | Start/Stop round | Unable to close round i.e. Round 1 - Open, button says 'Open Round 1' and Round 1 cannot be closed | Critical | 10 | 321 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
53 | 4 | Drop Bid | Drop bid' button not appearing on index.php | Critical | 10
54 | 4 | Start/Stop round | When Round 2 is closed, the button 'Open Round 1' is available and can be clicked to start Round 1 again | High | 5
55 | 4 | JSON Bootstrap | UAT test case 007-bootstrap - no errors expected but was given "class timetable clash" | High | 5
56 | 4 | JSON User Dump | UAT test case 008-user-dump - wrong edollar balance | High | 5
57 | 4 | JSON Update Bid | UAT test case 010-update-bid - no errors expected but was given "insufficient edollar" | High | 5
58 | 4 | JSON User Dump | UAT test case 011-user-dump - wrong edollar balance | High | 5
59 | 4 | JSON Dump | UAT test case 016-dump - tables dumped in the wrong order | High | 5
60 | 4 | JSON Dump | UAT test case 016-dump - "course" - "exam start" and "exam end" are in the wrong format | High | 5
61 | 4 | JSON Dump | UAT test case 016-dump - "section" - "start" and "end" are in the wrong format | High | 5
62 | 4 | JSON Dump | UAT test case 016-dump - "section" - "day" is in the wrong format | High | 5
63 | 4 | JSON Dump | UAT test case 016-dump - "section" - size is a string when it should be a number | High | 5
64 | 4 | JSON Dump | UAT test case 016-dump - "student" - edollar is a string when it should be a number | High | 5
65 | 4 | JSON Dump | UAT test case 016-dump - wrong heading name for course_completed - "course_completed" should be "completed-course" | High | 5
66 | 4 | JSON Update Bid | UAT test case 023-update-bid - no errors expected but got "class timetable clash" | High | 5
67 | 4 | JSON Section Dump | UAT test case 025-section-dump - expected data for 2 students but got 3 instead | High | 5
68 | 4 | JSON Section Dump | UAT test case 026-section-dump - expected data for 1 student but got 3 instead | High | 5
69 | 4 | JSON Bootstrap | UAT test case 027-bootstrap - wrong error message - expected "invalid course" but got "invalid code" | Low | 1
70 | 4 | JSON Bootstrap | UAT test case 027-bootstrap - wrong error message - expected "invalid amount" but got "invalid e-dollar" | Low | 1
71 | 4 | JSON Bootstrap | UAT test case 028-bootstrap - incorrect error thrown - expected "invalid size" but got "blank size" | High | 5
72 | 4 | JSON Bootstrap | UAT test case 029-bootstrap - wrong error message - expected "invalid course" but got "invalid code" | Low | 1
73 | 4 | JSON Bootstrap | UAT test case 029-bootstrap - error messages in wrong order | Low | 1
74 | 4 | JSON Bootstrap | UAT test case 031-bootstrap - incorrect error thrown for student.csv, causing 1 less row to be processed; got "blank e-dollar" when student should have been successfully processed | High | 5
75 | 4 | JSON Bootstrap | UAT test case 033-bootstrap - same "blank e-dollar" error as 031-bootstrap | High | 5
76 | 4 | JSON Bootstrap | UAT test case 033-bootstrap - unexpected errors "exam timetable clash" | High | 5
77 | 4 | JSON Update Bid | UAT test case 034-update-bid - expected errors [ "class timetable clash", "section limit reached" ] but got [ "class timetable clash", "exam timetable clash" ] instead | High | 5
78 | 4 | JSON Bootstrap | UAT test case 035-bootstrap - no errors expected but got "blank e-dollar" for student.csv and "exam timetable clash" for bid.csv | High | 5
79 | 4 | JSON Update Bid | UAT test case 036-update-bid - PDOException: Integrity constraint violation: 1452 Cannot add or update a child row: a foreign key constraint fails | Critical | 10
80 | 4 | JSON User Dump | UAT test case 037-user-dump - wrong e-dollar balance | High | 5
81 | 4 | JSON Update Bid | UAT test case 040-update-bid - no errors expected but got "insufficient e$" | High | 5
82 | 4 | JSON Stop | UAT test case 042-stop - Undefined offset: -1 on common.php line 469 | Critical | 10
83 | 4 | JSON Section Dump | UAT test case 043-section-dump - expected 1 student but got none | High | 5
84 | 4 | JSON Update Bid | UAT test case 050-update-bid - expected error "bid too low" but bid was updated successfully | High | 5
85 | 4 | JSON Update Bid | UAT test case 066-update-bid - no errors expected but got "insufficient e$" | High | 5
86 | 4 | JSON Bootstrap | UAT test case 067-bootstrap - wrong error message - expected "invalid course" but got "invalid code" | Low | 1
87 | 4 | JSON Bootstrap | UAT test case 067-bootstrap - error messages in wrong order | High | 5
88 | 4 | JSON Update Bid | UAT test case 069-update-bid - no errors expected but got "insufficient e$" | High | 5
89 | 4 | JSON Update Bid | UAT test case 074-update-bid - no errors expected but got "insufficient e$" | High | 5
90 | 4 | JSON Bid Dump | UAT test case 075-bid-dump - expected 1 student but got none | High | 5
91 | 4 | JSON Bid Dump | UAT test case 076-bid-dump - expected 2 students but got 3 | High | 5
92 | 4 | JSON User Dump | UAT test case 077-user-dump - wrong e-dollar balance | High | 5
93 | 4 | JSON Update Bid | UAT test case 084-update-bid - expected error "invalid amount" but got "bid too low" | High | 5
94 | 4 | JSON Bootstrap | UAT test case 109-bootstrap - expected error "invalid section" but row was successfully processed | High | 5
95 | 4 | JSON Bootstrap | UAT test case 112-bootstrap - incorrect error message - "invalid e-dollar" should be "invalid amount" | Low | 1
96 | 4 | JSON Bootstrap | UAT test case 121-bootstrap - incorrect error message - "invalid e-dollar" should be "invalid amount" | Low | 1
97 | 4 | JSON Drop Section | UAT test case 125-drop-section - incorrect error message - "round not active" should be "round ended" | Low | 1
98 | 4 | JSON Bootstrap | UAT test case 127-bootstrap - test case has an error, expected result should be error with "invalid section", but row was passed successfully | High | 5
99 | 4 | JSON Dump | UAT test case 138-dump - tables dumped in the wrong order | High | 5
100 | 4 | JSON Dump | UAT test case 138-dump - "course" - "exam start" and "exam end" are in the wrong format | High | 5
101 | 4 | JSON Dump | UAT test case 138-dump - "section" - "start" and "end" are in the wrong format | High | 5
102 | 4 | JSON Dump | UAT test case 138-dump - "section" - "day" is in the wrong format | High | 5
103 | 4 | JSON Dump | UAT test case 138-dump - "section" - size is a string when it should be a number | High | 5
104 | 4 | JSON Dump | UAT test case 138-dump - "student" - edollar is a string when it should be a number | High | 5
105 | 4 | JSON Dump | UAT test case 138-dump - wrong heading name for course_completed - "course_completed" should be "completed-course" | High | 5
106 | 4 | JSON Update Bid | UAT test case 146-update-bid - expected errors [ "class timetable clash", "course enrolled", "exam timetable clash" ] but only got [ "course enrolled"] | High | 5
107 | 4 | JSON Bootstrap | UAT test case 154-bootstrap - wrong error message - expected "invalid course" but got "invalid code" | Low | 1
108 | 4 | JSON Bootstrap | UAT test case 157-bootstrap - test case has an error, expected result should be error "exam timetable clash" but it was passed successfully | High | 5
109 | 4 | JSON Section Dump | UAT test case 169-section-dump - expected 1 student but got 2 | High | 5
110 | 4 | JSON Bid Dump | UAT test case 170-bid-dump - expected result "-" but got result "in" | High | 5
111 | 4 | Login | Login with incorrect credentials - expected UI error message but got console error "Array to string conversion in common.php on line 29" | High | 5
112 | 4 | Add Bid | UAT manual test case 2 - There is no way of knowing which school offers what courses on the course search table | Low | 1
113 | 4 | Add Bid | UAT manual test case 9 - E-dollar balance is not rounded off to 2dp | Low | 1
114 | 4 | Round2 logic clearing | UAT manual test case 18 - minimum bid not updated | High | 5
115 | 4 | Round2 logic clearing | UAT manual test case 19 - vacancies not updated | High | 5
116 | 4 | Round2 logic clearing | UAT manual test case 20 - minimum bid updated with the wrong amount | High | 5
117 | 4 | Round2 logic clearing | UAT manual test case 21 - expected fluffy's bid to be 'Success', got 'Fail' instead | High | 5
118 | 4 | Round2 logic clearing | UAT manual test case 21 - minimum bid not updating correctly | High | 5
119 | 4 | Round2 logic clearing | UAT manual test case 23 - expected fluffy's bid to pass but got 'Fail' instead | High | 5
120 | 4 | Round2 logic clearing | UAT manual test case 24 - expected error "invalid size" for section.csv line 14, but got "blank size" instead | High | 5
121 | 4 | Add Bid | UAT manual test case 9 - E-dollar balance is not rounded off to 2dp | Low | 1 | 265 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
122 | 5 | User Dump | Test case 036-user-dump - JSON common validations were in the wrong order | High | 5
123 | 5 | Dump | Test case 067-dump - Prerequisite array was empty | High | 5
124 | 5 | Dump | Test case 086-dump - Prerequisite array was empty | High | 5
125 | 5 | Start | Test case 092-start - Round number was in the wrong format | High | 5
126 | 5 | Dump | Test case 103-dump - Prerequisite array was empty | High | 5
127 | 5 | Update Bid | Test case 106-update-bid - Expected error "invalid amount" but got "success" instead | High | 5
128 | 5 | Update Bid | Test case 110-update-bid - Wrong error message - expected "invalid course" but got "invalid course code" | Low | 1
129 | 5 | Update Bid | Test case 112-update-bid - Section should not be validated if course code is invalid, but got all "missing" field validation errors (test case input error) | High | 5
130 | 5 | Update Bid | Test case 116-update-bid - Expected error "insufficient $e" but got "success" instead | Critical | 10
131 | 5 | Update Bid | Test case 117-update-bid - Expected 1 error but got 2 | High | 5
132 | 5 | Delete Bid | Test case 119-delete-bid: Call to a member function getR1Status() on null on delete-bid.php line 50 | Critical | 10
133 | 5 | User Dump | Test case 128-user-dump - Wrong e-dollar balance | High | 5
134 | 5 | Bid Status | Test case 129-bid-status - calvin.ng.2009 has wrong e-dollar balance | High | 5
135 | 5 | Dump | Test case 130-dump - ben.ng.2009 and calvin.ng.2009 have wrong e-dollar balance | High | 5
136 | 5 | Dump | Test case 130-dump - Prerequisite array was empty | High | 5
137 | 5 | Bid Status | Test case 141-bid-status - test case output error | Low | 1
138 | 5 | Dump | Test case 142-dump - Prerequisite array was empty | High | 5
139 | 5 | Dump | Test case 142-dump - wrong edollar balance for 'ben.ng.2009' | High | 5
140 | 5 | Start | Test case 144-start - test case output error | Low | 1
141 | 5 | Bid Status | Test case 145-bid-status - test case output error | Low | 1
142 | 5 | Dump | Test case 146-dump - Prerequisite array was empty | High | 5
143 | 5 | Dump | Test case 146-dump - ben.ng.2009 and calvin.ng.2009 have wrong e-dollar balance | High | 5
144 | 5 | Dump | Test case 154-dump - Prerequisite array was empty | High | 5
145 | 5 | Dump | Test case 154-dump - ben.ng.2009 and calvin.ng.2009 have wrong e-dollar balance | High | 5
146 | 5 | Update Bid | Test case 156-update-bid - Expected "success" but got error "insufficient e$" | High | 5
147 | 5 | Bid Status | Test case 159-bid-status - Expected 2 students but got 1 | High | 5
148 | 5 | Bid Status | Test case 161-bid-status - Expected 3 students but got 2 | High | 5
149 | 5 | Update Bid | Test case 162-update-bid - Expected "success" but got "bid too low" | High | 5
150 | 5 | Bid Status | Test case 163-bid-status - Expected students Ben, Calvin and Eddy but got Calvin, Dawn and Eddy | High | 5
151 | 5 | Bid Status | Test case 165-bid-status - Expected 4 students but got 3 | High | 5
152 | 5 | Bid Status | Test case 168-bid-status - Expected Parker, Dawn, Ben and Calvin but got Parker, Dawn, Calvin and Eddy | High | 5
153 | 5 | Bid Status | Test case 173-bid-status - Received information for wrong students | High | 5
154 | 5 | Bid Status | Test case 175-bid-status - Received information for wrong students | High | 5
155 | 5 | Bid Status | Test case 177-bid-status - Received information for wrong students | High | 5
156 | 5 | Bid Status | Test case 179-bid-status - Received information for wrong students | High | 5
157 | 5 | Bid Status | Test case 182-bid-status - Received information for wrong students | High | 5
158 | 5 | Bid Dump | Test case 184-bid-dump - Expected 5 students but got 4 | High | 5
159 | 5 | Dump | Test case 185-dump - Prerequisite array was empty | High | 5
160 | 5 | Dump | Test case 185-dump - Incorrect balance for ben.ng.2009 | High | 5
161 | 5 | Dump | Test case 185-dump - Incorrect bid information | High | 5
162 | 5 | Bid Dump | Test case 191-bid-dump - Incorrect students in bid information | High | 5
163 | 5 | Dump | Test case 195-dump - Incorrect bid information | High | 5
164 | 5 | Dump | Test case 195-dump - Incorrect balance for ben.ng.2009 | High | 5
165 | 5 | Dump | Test case 195-dump - Prerequisite array was empty | High | 5
166 | 5 | User Dump | Test case 196-user-dump - Incorrect e$ balance for ben.ng.2009 | High | 5
167 | 5 | Bid Status | Logic for minimum bid when round 2 is closed is wrong; API gets lowest bid across round 1 and round 2 but should get lowest bid from round 2 instead | High | 5
168 | 5 | Update Bid | Test case 112-update-bid - Section should not be validated if course code is invalid, but got all "missing" field validation errors (test case input error) | High | 5
169 | 5 | Delete Bid | Test case 119-delete-bid: Call to a member function getR1Status() on null on delete-bid.php line 50 | Critical | 10
170 | 5 | Bid Status | Test case 129-bid-status - test case output error | Low | 1
171 | 5 | Bid Status | Test case 141-bid-status - test case output error | Low | 1
172 | 5 | Start | Test case 144-start - test case output error | Low | 1
173 | 5 | Bid Status | Test case 145-bid-status - test case output error | Low | 1
174 | 5 | Add Bid | Link to 'Plan&Bid' page is missing | Critical | 10
175 | 5 | Login | Unexpected 'else' in common.php | Critical | 10
176 | 5 | Index | Information about round number, status and student edollar balance is repeated on home page | Low | 1
177 | 5
178 | 5
179 | 5
180 | 5
181 | 5
182 | 5
183 | 5
184 | 5
185 | 5
186 | 5
187 | 5
188 | 5
189 | 5
190 | 5
191 | 5
192 | 5
193 | 5
194 | 5
195 | 5
196 | 5
197 | 5
198 | 5
199 | 5
200 | 5
201 | 5
202 | 5
203 | 5

## Bug Log
Bug Log
S/N | Iteration | Function | Description | Status | Discovered On | Resolved On | Fixed by (PP Team)
1 | 1 | Login (Student) | Successful login brought the user to 'Plan Bid' page instead of the student home page | Resolved | 2017-10-01 | 2017-10-01 | HS & SL
2 | 1 | Login (Student) | User name displayed on home page did not change according to the user that logged in | Resolved | 2017-10-01 | 2017-10-01 | HS & SL
3 | 1 | Login (Admin) | Admin got directed to student home page instead of bidding admin page and hence causing error and causes login to be unsuccessful | Resolved | 2017-10-01 | 2017-10-01 | HS & SL
4 | 1 | Login (Admin) | Admin is able to login successfully when they key in their password in caps | Resolved | 2017-10-01 |  | HS & SL
5 | 1 | Login (Student) | Student is able to login successfully when they select their role as admin and was brought to the bidding admin page | Resolved | 2017-10-01 | 2017-10-01 | HS & SL
6 | 2 | Add Bid | Your bid was placed successfully!' was displayed instead of the expected error message when student enters non-existing course code | Resolved | 2017-10-01 | 2017-10-04 | JM & ST
7 | 2 | Add Bid | Student was able to bid for course that are not offered by their school during round 1 | Resolved | 2017-10-04 | 2017-10-05 | JM & ST
8 | 2 | Add Bid | Student was able to bid for courses where they have not fulfilled the necessary pre-requisite course(s) | Resolved | 2017-10-05 | 13/10/2017 | JM & ST
9 | 2 | Bootstrap | SQL error: Tables could not be truncated due to foreign key constraints | Resolved | 2019-10-15 | 2019-10-15 | HS & ST
10 | 2 | Bootstrap | Incorrect variable name | Resolved | 2019-10-15 | 2019-10-15 | HS & ST
11 | 2 | Bootstrap | Error due to calling class methods inside a PDO function | Resolved | 2019-10-15 | 2019-10-15 | HS & ST
12 | 2 | Bootstrap | Too few arguments in 'validateDate()' | Resolved | 2019-10-15 | 2019-10-15 | HS & ST
13 | 2 | Bootstrap | SQL error: Column not found (used wrong column name) | Resolved | 2019-10-15 | 2019-10-15 | HS & ST
14 | 2 | Bootstrap | Issue with the validateDate() function in common.php, causing all exam dates to be invalid | Resolved | 2019-10-15 | 2019-10-15 | HS & ST
15 | 2 | Bootstrap | Incorrect row numbers shown in bootstrap errors | Resolved | 2019-10-15 | 2019-10-15 | HS & ST
16 | 2 | Drop Bid | Cannot access private property Student::$edollar | Resolved | 2019-10-15 | 2019-10-15 | HS & SL
17 | 2 | Drop Bid | After dropping bid, updated e$ amount is not displayed | Resolved | 2019-10-15 | 2019-10-16 | SL & HY
18 | 2 | Bootstrap | Undefined variable: getCourse | Resolved | 2019-10-16 | 2019-10-16 | SL & HY
19 | 2 | Bootstrap | Call to undefined method Prerequisite::getUserid() in CourseCompletedDAO.php | Resolved | 2019-10-16 | 2019-10-16 | SL & HY
20 | 2 | Bootstrap | Too few arguments for function $sectionDAO->retrieve() on line 538 | Resolved | 2019-10-16 | 2019-10-16 | SL & HY
21 | 2 | Bootstrap | Undefined variable: alreadyBidded | Resolved | 2019-10-16 | 2019-10-16 | SL & HY
22 | 2 | Bootstrap | SQL error: Failed to update due to the use of wrong variable name | Resolved | 2019-10-16 | 2019-10-16 | SL & HY
23 | 2 | Bootstrap | SQL error: duplicate entry due to incorrect validations against bid for same section | Resolved | 2019-10-16 | 2019-10-16 | SL & HY
24 | 2 | Bootstrap | Edollar balance not updated in database | Resolved | 2019-10-16 | 2019-10-16 | SL & HY
25 | 2 | Bootstrap | Edollar balance not updated in database | Resolved | 2019-10-16 | 2019-10-16 | SL & HY
26 | 2 | Bootstrap | Bootstrap succesful but error are not reported when the pre-requisite course has yet to be attempted | Resolved | 2019-10-16 | 2019-10-16 | SL & HY
27 | 2 | Bootstrap | Bootstrap successful but error not displayed when amount in bidded is less than e$10 | Resolved | 2019-10-16 | 2019-10-16 | SL & HY
28 | 2 | Bootstrap | Bootstrap unsuccessful and bid has entered the database when the amount in bid is less than e$10 | Resolved | 2019-10-16 | 2019-10-16 | SL & HY
29 | 2 | Bootstrap | No error displayed for when student is unable to place bids when there is insufficient e$ | Resolved | 2019-10-16 | 2019-10-16 | SL & HY
30 | 2 | Bootstrap | Bootstrap unsuccessful due to incorrect data input in the bootstrap folder | Resolved | 2019-10-16 | 2019-10-16 | SL & HY
31 | 3 | JSON Authenticate | Entered correct admin credentials, but was shown 'error: userid cannot be empty' | Resolved | 2019-10-29 | 2019-10-29 | JM & ST
32 | 3 | JSON Authenticate | Incorrect error messages displayed | Resolved | 2019-10-29 | 2019-10-29 | JM & ST
33 | 3 | JSON Start | Redirected to login.php | Resolved | 2019-10-29 | 2019-10-29 | JM & ST
34 | 3 | JSON Start | Round 2 was started when round 1 was already started | Resolved | 2019-10-29 | 2019-10-29 | JM & ST
35 | 3 | JSON Stop | Invalid offset in processBids() function | Resolved | 2019-10-29 | 2019-10-29 | JM & ST
36 | 3 | JSON Stop | Undefined variable: UpdateStatusOK | Resolved | 2019-10-29 | 2019-10-29 | JM & ST
37 | 3 | JSON Update Bid | API was taking in POST parameters instead of GET | Resolved | 2019-10-29 | 2019-10-29 | JM & ST
38 | 3 | JSON Update Bid | Only one error message displayed when many were expected | Resolved | 2019-10-29 | 2019-10-29 | JM & ST
| 3 | JSON Update Bid | Error displayed due to existing bid when the existing bid should be updated | Resolved | 2019-10-29 | 2019-10-29 | JM & ST
| 3 | JSON Update Bid | array_values() expects parameter 1 to be array, boolean given on line number 2 | Resolved | 2019-10-29 | 2019-10-29 | JM & ST
| 3 | JSON Delete Bid | Only one error message displayed when many were expected (wrong syntax for appending error messages to array) | Resolved | 2019-10-29 | 2019-10-29 | JM & ST
| 3 | JSON Delete Bid | Undefined variable: student | Resolved | 2019-10-29 | 2019-10-29 | JM & ST
| 3 | JSON Delete Bid | Undefined variable: biddedamount | Resolved | 2019-10-29 | 2019-10-29 | JM & ST
| 3 | JSON Delete Bid | Section could be dropped when only pending bids should be dropped | Resolved | 2019-10-29 | 2019-10-29 | JM & ST
| 3 | JSON Delete Section | Only one error message displayed when many were expected | Resolved | 2019-10-29 | 2019-10-29 | JM & ST
| 3 | JSON Dump Bid | Entered valid inputs, but was given 'error' with 'null' messages | Resolved | 2019-10-29 | 2019-10-29 | JM & ST
| 3 | JSON Dump Section | Wrong error message for common validations | Resolved | 2019-10-29 | 2019-10-29 | JM & ST
| 3 | Round2 logic clearing | Bidding results not displayed when round 2 is closed | Resolved | 2019-10-29 | 2019-10-29 | HY & JM
| 3 | Round2 logic clearing | Unable to drop section (from successful bid in round 1) when round 2 is open | Resolved | 2019-10-29 | 2019-10-29 | HY & JM
| 3 | Round2 logic clearing | Placing bid is successful when the exam timetable clash | Resolved | 2019-10-29 | 2019-10-29 | HY & JM
| 3 | Round2 logic clearing | Able to place bids for same course and section already bidded succesfully in round 1 (status: Success) regardless of vacancy | Resolved | 2019-10-29 | 2019-10-29 | HY & JM
| 4 | Start/Stop round | Unable to close round i.e. Round 1 - Open, button says 'Open Round 1' and Round 1 cannot be closed | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | Drop Bid | Drop bid' button not appearing on index.php | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | Start/Stop round | When Round 2 is closed, the button 'Open Round 1' is available and can be clicked to start Round 1 again | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Bootstrap | UAT test case 007-bootstrap - no errors expected but was given "class timetable clash" | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON User Dump | UAT test case 008-user-dump - wrong edollar balance | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Update Bid | UAT test case 010-update-bid - no errors expected but was given "insufficient edollar" | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON User Dump | UAT test case 011-user-dump - wrong edollar balance | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Dump | UAT test case 016-dump - tables dumped in the wrong order | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Dump | UAT test case 016-dump - "course" - "exam start" and "exam end" are in the wrong format | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Dump | UAT test case 016-dump - "section" - "start" and "end" are in the wrong format | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Dump | UAT test case 016-dump - "section" - "day" is in the wrong format | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Dump | UAT test case 016-dump - "section" - size is a string when it should be a number | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Dump | UAT test case 016-dump - "student" - edollar is a string when it should be a number | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Dump | UAT test case 016-dump - wrong heading name for course_completed - "course_completed" should be "completed-course" | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Update Bid | UAT test case 023-update-bid - no errors expected but got "class timetable clash" | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Section Dump | UAT test case 025-section-dump - expected data for 2 students but got 3 instead | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Section Dump | UAT test case 026-section-dump - expected data for 1 student but got 3 instead | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Bootstrap | UAT test case 027-bootstrap - wrong error message - expected "invalid course" but got "invalid code" | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Bootstrap | UAT test case 027-bootstrap - wrong error message - expected "invalid amount" but got "invalid e-dollar" | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Bootstrap | UAT test case 028-bootstrap - incorrect error thrown - expected "invalid size" but got "blank size" | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Bootstrap | UAT test case 029-bootstrap - wrong error message - expected "invalid course" but got "invalid code" | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Bootstrap | UAT test case 029-bootstrap - error messages in wrong order | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Bootstrap | UAT test case 031-bootstrap - incorrect error thrown for student.csv, causing 1 less row to be processed; got "blank e-dollar" when student should have been successfully processed | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Bootstrap | UAT test case 033-bootstrap - same "blank e-dollar" error as 031-bootstrap | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Bootstrap | UAT test case 033-bootstrap - unexpected errors "exam timetable clash" | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Update Bid | UAT test case 034-update-bid - expected errors [ "class timetable clash", "section limit reached" ] but got [ "class timetable clash", "exam timetable clash" ] instead | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Bootstrap | UAT test case 035-bootstrap - no errors expected but got "blank e-dollar" for student.csv and "exam timetable clash" for bid.csv | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Update Bid | UAT test case 036-update-bid - PDOException: Integrity constraint violation: 1452 Cannot add or update a child row: a foreign key constraint fails | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON User Dump | UAT test case 037-user-dump - wrong e-dollar balance | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Update Bid | UAT test case 040-update-bid - no errors expected but got "insufficient e$" | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Stop | UAT test case 042-stop - Undefined offset: -1 on common.php line 469 | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Section Dump | UAT test case 043-section-dump - expected 1 student but got none | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Update Bid | UAT test case 050-update-bid - expected error "bid too low" but bid was updated successfully | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Update Bid | UAT test case 066-update-bid - no errors expected but got "insufficient e$" | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Bootstrap | UAT test case 067-bootstrap - wrong error message - expected "invalid course" but got "invalid code" | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Bootstrap | UAT test case 067-bootstrap - error messages in wrong order | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Update Bid | UAT test case 069-update-bid - no errors expected but got "insufficient e$" | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Update Bid | UAT test case 074-update-bid - no errors expected but got "insufficient e$" | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Bid Dump | UAT test case 075-bid-dump - expected 1 student but got none | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Bid Dump | UAT test case 076-bid-dump - expected 2 students but got 3 | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON User Dump | UAT test case 077-user-dump - wrong e-dollar balance | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Update Bid | UAT test case 084-update-bid - expected error "invalid amount" but got "bid too low" | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Bootstrap | UAT test case 109-bootstrap - expected error "invalid section" but row was successfully processed | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Bootstrap | UAT test case 112-bootstrap - incorrect error message - "invalid e-dollar" should be "invalid amount" | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Bootstrap | UAT test case 121-bootstrap - incorrect error message - "invalid e-dollar" should be "invalid amount" | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Drop Section | UAT test case 125-drop-section - incorrect error message - "round not active" should be "round ended" | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Bootstrap | UAT test case 127-bootstrap - test case has an error, expected result should be error with "invalid section", but row was passed successfully | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Dump | UAT test case 138-dump - tables dumped in the wrong order | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Dump | UAT test case 138-dump - "course" - "exam start" and "exam end" are in the wrong format | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Dump | UAT test case 138-dump - "section" - "start" and "end" are in the wrong format | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Dump | UAT test case 138-dump - "section" - "day" is in the wrong format | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Dump | UAT test case 138-dump - "section" - size is a string when it should be a number | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Dump | UAT test case 138-dump - "student" - edollar is a string when it should be a number | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Dump | UAT test case 138-dump - wrong heading name for course_completed - "course_completed" should be "completed-course" | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Update Bid | UAT test case 146-update-bid - expected errors [ "class timetable clash", "course enrolled", "exam timetable clash" ] but only got [ "course enrolled"] | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Bootstrap | UAT test case 154-bootstrap - wrong error message - expected "invalid course" but got "invalid code" | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Bootstrap | UAT test case 157-bootstrap - test case has an error, expected result should be error "exam timetable clash" but it was passed successfully | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Section Dump | UAT test case 169-section-dump - expected 1 student but got 2 | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | JSON Bid Dump | UAT test case 170-bid-dump - expected result "-" but got result "in" | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | Login | Login with incorrect credentials - expected UI error message but got console error "Array to string conversion in common.php on line 29" | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | Add Bid | UAT manual test case 2 - There is no way of knowing which school offers what courses on the course search table | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | Add Bid | UAT manual test case 9 - E-dollar balance is not rounded off to 2dp | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | Round2 logic clearing | UAT manual test case 18 - minimum bid not updated | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | Round2 logic clearing | UAT manual test case 19 - vacancies not updated | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | Round2 logic clearing | UAT manual test case 20 - minimum bid updated with the wrong amount | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | Round2 logic clearing | UAT manual test case 21 - expected fluffy's bid to be 'Success', got 'Fail' instead | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | Round2 logic clearing | UAT manual test case 21 - minimum bid not updating correctly | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | Round2 logic clearing | UAT manual test case 23 - expected fluffy's bid to pass but got 'Fail' instead | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 4 | Round2 logic clearing | UAT manual test case 24 - expected error "invalid size" for section.csv line 14, but got "blank size" instead | Resolved | 2019-11-13 | 2019-11-14 | ST & SL
| 5 | Add Bid | UAT manual test case 9 - E-dollar balance is not rounded off to 2dp | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Dump | Test case 067-dump - Prerequisite array was empty | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Dump | Test case 086-dump - Prerequisite array was empty | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Start | Test case 092-start - Round number was in the wrong format | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Dump | Test case 103-dump - Prerequisite array was empty | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Update Bid | Test case 106-update-bid - Expected error "invalid amount" but got "success" instead | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Update Bid | Test case 110-update-bid - Wrong error message - expected "invalid course" but got "invalid course code" | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Update Bid | Test case 112-update-bid - Section should not be validated if course code is invalid, but got all "missing" field validation errors (test case input error) | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Update Bid | Test case 116-update-bid - Expected error "insufficient $e" but got "success" instead | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Update Bid | Test case 117-update-bid - Expected 1 error but got 2 | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Delete Bid | Test case 119-delete-bid: Call to a member function getR1Status() on null on delete-bid.php line 50 | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | User Dump | Test case 128-user-dump - Wrong e-dollar balance | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Bid Status | Test case 129-bid-status - calvin.ng.2009 has wrong e-dollar balance | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Dump | Test case 130-dump - ben.ng.2009 and calvin.ng.2009 have wrong e-dollar balance | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Dump | Test case 130-dump - Prerequisite array was empty | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Bid Status | Test case 141-bid-status - test case output error | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Dump | Test case 142-dump - Prerequisite array was empty | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Dump | Test case 142-dump - wrong edollar balance for 'ben.ng.2009' | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Start | Test case 144-start - test case output error | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Bid Status | Test case 145-bid-status - test case output error | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Dump | Test case 146-dump - Prerequisite array was empty | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Dump | Test case 146-dump - ben.ng.2009 and calvin.ng.2009 have wrong e-dollar balance | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Dump | Test case 154-dump - Prerequisite array was empty | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Dump | Test case 154-dump - ben.ng.2009 and calvin.ng.2009 have wrong e-dollar balance | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Update Bid | Test case 156-update-bid - Expected "success" but got error "insufficient e$" | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Bid Status | Test case 159-bid-status - Expected 2 students but got 1 | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Bid Status | Test case 161-bid-status - Expected 3 students but got 2 | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Update Bid | Test case 162-update-bid - Expected "success" but got "bid too low" | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Bid Status | Test case 163-bid-status - Expected students Ben, Calvin and Eddy but got Calvin, Dawn and Eddy | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Bid Status | Test case 165-bid-status - Expected 4 students but got 3 | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Bid Status | Test case 168-bid-status - Expected Parker, Dawn, Ben and Calvin but got Parker, Dawn, Calvin and Eddy | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Bid Status | Test case 173-bid-status - Received information for wrong students | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Bid Status | Test case 175-bid-status - Received information for wrong students | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Bid Status | Test case 177-bid-status - Received information for wrong students | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Bid Status | Test case 179-bid-status - Received information for wrong students | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Bid Status | Test case 182-bid-status - Received information for wrong students | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Bid Dump | Test case 184-bid-dump - Expected 5 students but got 4 | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Dump | Test case 185-dump - Prerequisite array was empty | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Dump | Test case 185-dump - Incorrect balance for ben.ng.2009 | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Dump | Test case 185-dump - Incorrect bid information | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Bid Dump | Test case 191-bid-dump - Incorrect students in bid information | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Dump | Test case 195-dump - Incorrect bid information | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Dump | Test case 195-dump - Incorrect balance for ben.ng.2009 | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Dump | Test case 195-dump - Prerequisite array was empty | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | User Dump | Test case 196-user-dump - Incorrect e$ balance for ben.ng.2009 | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Bid Status | Logic for minimum bid when round 2 is closed is wrong; API gets lowest bid across round 1 and round 2 but should get lowest bid from round 2 instead | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Update Bid | Test case 112-update-bid - Section should not be validated if course code is invalid, but got all "missing" field validation errors (test case input error) | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Delete Bid | Test case 119-delete-bid: Call to a member function getR1Status() on null on delete-bid.php line 50 | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Bid Status | Test case 129-bid-status - test case output error | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Bid Status | Test case 141-bid-status - test case output error | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Start | Test case 144-start - test case output error | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Bid Status | Test case 145-bid-status - test case output error | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Add Bid | Link to 'Plan&Bid' page is missing | Resolved | 2019-11-16 | 2019-11-17 | HS & ST
| 5 | Login | Unexpected 'else' in common.php | Resolved | 2019-11-17 | 2019-11-17 | ST & JM
| 5 | Index | Information about round number, status and student edollar balance is repeated on home page
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5
5