## Week 5
Person | Question | Week: 16/09/2019 to 22/09/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Xin Rong, Steffi | What did you do yesterday? |  |  |  |  | Met and discussed the schedule and assigned roles for this iteration | Edited schedule | Edited schedule
| What will you do today? |  |  |  |  | Continue updating the schedule | Continue updating the schedule | Continue updating the schedule
| Do you have any obstacles? |  |  |  |  | None | None | None
Lim Jie Min | What did you do yesterday? |  |  |  |  | Planned schedule with the team | Not a working day | Not a working day
| What will you work on today? |  |  |  |  | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? |  |  |  |  | NA | NA | NA
Lim Hui Sin | What did you do yesterday? |  |  |  |  | Met with team to plan schedule | Not a working day | Not a working day
| What will you work on today? |  |  |  |  | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? |  |  |  |  | NA | NA | NA
Ku Seoung Lim | What did you do yesterday? |  |  |  |  | Team meeting | Not a working day | Not a working day
| What will you work on today? |  |  |  |  | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? |  |  |  |  | NA | NA | NA
Hilya Syazwani Binte Mohamed Yusoff | What did you do yesterday? |  |  |  |  | Attended meeting to discuss schedule, committed and pushed the minutes to repo | Not a working day | Not a working day
| What will you work on today? |  |  |  |  | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? |  |  |  |  | NA | NA | NA

## Week 6
Person | Question | Week: 23/09/2019 to 29/09/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Xin Rong, Steffi | What did you do yesterday? | Edited schedule, daily updates | Edited schedule, daily updates, team meeting | Edited schedule, daily updates | Edited schedule, daily updates | Edited schedule, daily updates | Edited schedule, daily updates
| What will you do today? | Edit schedule, daily updates, team meeting | Edit schedule, daily updates | Continue updating the schedule, daily updates | Continue updating the schedule, daily updates | Continue updating the schedule, daily updates | Continue updating the schedule, daily updates
| Do you have any obstacles? | None | None | None | None | None | None
Lim Jie Min | What did you do yesterday? | Not a working day | Coded login page | Not a working day | Not a working day | Not a working day | Not a working day
| What will you work on today? | Team meeting, PP for login page | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | None | NA | NA | NA | NA | NA
Lim Hui Sin | What did you do yesterday? | Not a working day | Created SQL database, coded classes and DAOs, created bootstrap.php | Not a working day | Not a working day | Not a working day | Not a working day
| What will you work on today? | Team meeting, PP for login page | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | None | NA | NA | NA | NA | NA
Ku Seoung Lim | What did you do yesterday? | Not a working day | Created SQL database, coded classes and DAOs, created bootstrap.php | Not a working day | Not a working day | Not a working day | Not a working day
| What will you work on today? | Team meeting, PP for bootstrap | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | None | NA | NA | NA | NA | NA
Hilya Syazwani Binte Mohamed Yusoff | What did you do yesterday? | Not a working day | Coded login page | Not a working day | Not a working day | Not a working day | Not a working day
| What will you work on today? | Team meeting, PP for bootstrap | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | None | NA | NA | NA | NA | NA

## Week 7
Person | Question | Week: 30/09/2019 to 06/10/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Xin Rong, Steffi | What did you do yesterday?
What will you do today?
Do you have any obstacles?
Lim Jie Min | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Lim Hui Sin | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Ku Seoung Lim | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Hilya Syazwani Binte Mohamed Yusoff | What did you do yesterday?
What will you work on today?
Do you have any obstacles?

## Week 8
Person | Question | Week: 07/10/2019 to 13/10/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Xin Rong, Steffi | What did you do yesterday?
What will you do today?
Do you have any obstacles?
Lim Jie Min | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Lim Hui Sin | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Ku Seoung Lim | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Hilya Syazwani Binte Mohamed Yusoff | What did you do yesterday?
What will you work on today?
Do you have any obstacles?

## Week 9
Person | Question | Week: 14/10/2019 to 20/10/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Xin Rong, Steffi | What did you do yesterday?
What will you do today?
Do you have any obstacles?
Lim Jie Min | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Lim Hui Sin | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Ku Seoung Lim | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Hilya Syazwani Binte Mohamed Yusoff | What did you do yesterday?
What will you work on today?
Do you have any obstacles?

## Week 10
Person | Question | Week: 21/10/2019 to 27/10/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Xin Rong, Steffi | What did you do yesterday?
What will you do today?
Do you have any obstacles?
Lim Jie Min | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Lim Hui Sin | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Ku Seoung Lim | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Hilya Syazwani Binte Mohamed Yusoff | What did you do yesterday?
What will you work on today?
Do you have any obstacles?

## Week 11
Person | Question | Week: 28/10/2019 to 03/11/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Xin Rong, Steffi | What did you do yesterday?
What will you do today?
Do you have any obstacles?
Lim Jie Min | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Lim Hui Sin | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Ku Seoung Lim | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Hilya Syazwani Binte Mohamed Yusoff | What did you do yesterday?
What will you work on today?
Do you have any obstacles?

## Week 12
Person | Question | Week: 04/11/2019 to 10/11/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Xin Rong, Steffi | What did you do yesterday?
What will you do today?
Do you have any obstacles?
Lim Jie Min | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Lim Hui Sin | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Ku Seoung Lim | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Hilya Syazwani Binte Mohamed Yusoff | What did you do yesterday?
What will you work on today?
Do you have any obstacles?

## Week 13
Person | Question | Week: 11/11/2019 to 17/11/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Xin Rong, Steffi | What did you do yesterday?
What will you do today?
Do you have any obstacles?
Lim Jie Min | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Lim Hui Sin | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Ku Seoung Lim | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Hilya Syazwani Binte Mohamed Yusoff | What did you do yesterday?
What will you work on today?
Do you have any obstacles?