## Week 5
Person | Question | Week: 16/09/2019 to 22/09/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Xin Rong, Steffi | What did you do yesterday? |  |  |  |  | Met and discussed the schedule and assigned roles for this iteration | Edited schedule | Edited schedule
| What will you do today? |  |  |  |  | Continue updating the schedule | Continue updating the schedule | Continue updating the schedule
| Do you have any obstacles? |  |  |  |  | None | None | None
Lim Jie Min | What did you do yesterday? |  |  |  |  | Planned schedule with the team | Not a working day | Not a working day
| What will you work on today? |  |  |  |  | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? |  |  |  |  | NA | NA | NA
Lim Hui Sin | What did you do yesterday? |  |  |  |  | Met with team to plan schedule | Not a working day | Not a working day
| What will you work on today? |  |  |  |  | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? |  |  |  |  | NA | NA | NA
Ku Seoung Lim (Sky) | What did you do yesterday? |  |  |  |  | Team meeting | Not a working day | Not a working day
| What will you work on today? |  |  |  |  | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? |  |  |  |  | NA | NA | NA
Hilya Syazwani Binte Mohamed Yusoff | What did you do yesterday? |  |  |  |  | Attended meeting to discuss schedule, committed and pushed the minutes to repo | Not a working day | Not a working day
| What will you work on today? |  |  |  |  | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? |  |  |  |  | NA | NA | NA

## Week 6
Person | Question | Week: 23/09/2019 to 29/09/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Xin Rong, Steffi | What did you do yesterday? | Edited schedule, daily updates | Edited schedule, daily updates, team meeting | Edited schedule, daily updates | Edited schedule, daily updates | Edited schedule, daily updates | Edited schedule, daily updates | Edited schedule, daily updates
| What will you do today? | Edit schedule, daily updates, team meeting | Edit schedule, daily updates | Continue updating the schedule, daily updates | Continue updating the schedule, daily updates | Continue updating the schedule, daily updates | Continue updating the schedule, daily updates | Continue updating the schedule, daily updates
| Do you have any obstacles? | None | None | None | None | None | None | None
Lim Jie Min | What did you do yesterday? | Not a working day | Coded login page with hilya | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| What will you work on today? | Team meeting, PP for login page | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | None | NA | NA | NA | NA | NA | NA
Lim Hui Sin | What did you do yesterday? | Not a working day | Created SQL database, coded classes and DAOs, created bootstrap.php with sky | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| What will you work on today? | Team meeting, PP for login page | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | None | NA | NA | NA | NA | NA | NA
Ku Seoung Lim (Sky) | What did you do yesterday? | Not a working day | Created SQL database, coded classes and DAOs, created bootstrap.php with sky | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| What will you work on today? | Team meeting, PP for bootstrap | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | None | NA | NA | NA | NA | NA | NA
Hilya Syazwani Binte Mohamed Yusoff | What did you do yesterday? | Not a working day | Coded login page with jm | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| What will you work on today? | Team meeting, PP for bootstrap | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | None | NA | NA | NA | NA | NA | NA

## Week 7
Person | Question | Week: 30/09/2019 to 06/10/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Xin Rong, Steffi | What did you do yesterday? | Edited schedule, daily updates | Edited schedule, daily updates | Overhauled the schedule and planned until the end of the project, held team meeting to ensure everyone is on the same page. Daily update | Finalised schedule, worked on slides | Deployed app, submitted slides and did PM Review | Helped with adjusting schedule | Helped with scheduling, fixed admin login
| What will you do today? | Prepare PM Review slides, Update schedule, daily updates | Team meeting, update schedule until end of project, daily updates | Simplify tasks on schedule as there is too much detail. Will draw critical path and prepare slides for PM review | Deploy app, submit slides, PM Review | Revisit scheduling | Help with scheduling, fix admin login | Helped with scheduling
| Do you have any obstacles? | None | None | None | I haven’t tried deploying the app before, so hopefully there are no delays | None | None | None
Lim Jie Min | What did you do yesterday? | Not a working day | Finished all bootstrap validations up to course_completed with hs | Attended the team meeting, helped to write the login test cases and updated the bug metrics | Added more DAO functions and implemented login for admin | Attended PM Review | Not a working day | Not a working day
| What will you work on today? | Complete bootstrap.php validations | Team meeting, write test cases for login, add to bug metrics | Add more DAO functions and add the login page for admin. | PM Review | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | None | None | None | None | None | None | None
Lim Hui Sin | What did you do yesterday? | Not a working day | Finished all bootstrap validations up to course_completed with jm | I went for the team meeting, ran the test cases to test login and debugged the code. | Updated the DAOs and finished login for the admin | Helped with slides and PM Review | Adjusting schedule, daily updates | Adjusting schedule, daily updates
| What will you work on today? | Continue and finish coding bootstrap.php and bootstrapping validations | Team meeting, test login functionality, debugging | Implement more methods in our DAOs and code the login functionality for the admin. | I'll help with the slides and attend the PM Review | Revisit scheduling | Revisit schedule, daily updates | Continue updating the schedule, daily updates
| Do you have any obstacles? | None | None | None | None | None | None | None
Ku Seoung Lim (Sky) | What did you do yesterday? | Not a working day | Created bidding results summary table for student home page, began coding 'plan bid' page with hilya | Attended team meeting. Clarify project requirements I wasn't sure about. Also helped to test login and debug the code. | Not a working day | Drew critical paths for the slides, attended PM Review | Not a working day | Fixed admin login
| What will you work on today? | Update student login landing page, coding bootstrap form for admin page | Team meeting, test login functionality, debugging | Not a working day | I will draw the critical paths for the slides, PM review | Not a working day | Fix admin login | Not a working day
| Do you have any obstacles? | None | None | None | None | None | None | None
Hilya Syazwani Binte Mohamed Yusoff | What did you do yesterday? | Not a working day | Created bidding results summary table for student home page, started on 'plan bid' page with sky | Not a working day | Not a working day | Attended PM Review | Not a working day | Not a working day
| What will you work on today? | Creating bidding summary table for studen'ts landing page, creating admin's page for bootstrapping | Not a working day | Not a working day | PM Review | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | None | None | None | None | None | None | None

## Week 8
Person | Question | Week: 07/10/2019 to 13/10/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Xin Rong, Steffi | What did you do yesterday? | Helped with scheduling | Completed admin bootstrap, added necessary methods to classes and DAOs with sky | Added logic validations for course_completed.csv,Implement 'add bid' functionality except validations for timetable clashes, created process_placebid.php with hs | Not a working day | Not a working day | Completed 'add bid' functionality with sky | Not a working day
| What will you do today? | Complete admin bootstrap, Add necessary methods to classes and DAOs with sky | Write test cases for 'drop bid' and 'drop section' functionality, implement 'add bid' functionality | Not a working day | Not a working day | Complete 'add bid' functionality with sky | Not a working day | Not a working day
| Do you have any obstacles? | None | None | None | None | None | None | None
Lim Jie Min | What did you do yesterday? | Not a working day | Not a working day | Add necessary methods to classes and DAOs except UpdateEdollar() in StudentDAO class, implemented 'open / close round' functionality with hilya | Not a working day | Implemented 'drop bid' and 'drop section' functionality with hilya | Wrote test cases for 'add bid' functionality and tested 'add bid' functionality with hilya | Wrote some test cases for bootstrap with sky
| What will you work on today? | Not a working day | Implement 'drop bid' and 'drop section' functionality | Not a working day | Implement 'drop bid' and 'drop section' functionality with hilya | Write test cases for 'add bid' functionality with hilya | Write test cases for bootstrap with sky | Not a working day
| Do you have any obstacles? | None | None | None | None | None | None | None
Lim Hui Sin | What did you do yesterday? | Adjusting schedule, daily updates | Adjusting schedule, daily updates | Adjusting schedule, daily updates, added logic validations for course_completed.csv,Implement 'add bid' functionality except validations for timetable clashes, created process_placebid.php with steffi | Adjusting schedule, daily updates | Adjusting schedule, daily updates | Adjusting schedule, daily updates | Adjusting schedule, daily updates, did not manage to debug 'drop bid' and 'drop section' functionality
| What will you work on today? | Continue updating the schedule, daily updates | Continue updating the schedule, daily updates, write test cases for 'drop bid' and 'drop section' functionality, implement 'add bid' functionality | Continue updating the schedule, daily updates | Continue updating the schedule, daily updates | Continue updating the schedule, daily updates | Continue updating the schedule, daily updates, debugging 'drop bid' and 'drop section' functionality | Continue updating the schedule, daily updates
| Do you have any obstacles? | None | None | None | None | None | None | None
Ku Seoung Lim (Sky) | What did you do yesterday? | Not a working day | Completed admin bootstrap, added necessary methods to classes and DAOs with steffi | Not a working day | Not a working day | Not a working day | Completed 'add bid' functionality with steffi | Wrote some test cases for bootstrap with jm
| What will you work on today? | Complete admin bootstrap, Add necessary methods to classes and DAOs with steffi | Not a working day | Not a working day | Not a working day | Complete 'add bid' functionality with steffi | Write test cases for bootstrap with jm | Not a working day
| Do you have any obstacles? | None | None | None | None | None | None | None
Hilya Syazwani Binte Mohamed Yusoff | What did you do yesterday? | Not a working day | Not a working day | Add necessary methods to classes and DAOs except UpdateEdollar() in StudentDAO class, implemented 'open / close round' functionality with jm | Not a working day | Implemented 'drop bid' and 'drop section' functionality with jm | Wrote test cases for 'add bid' functionality and tested 'add bid' functionality with jm | Not a working day
| What will you work on today? | Not a working day | Implement 'drop bid' and 'drop section' functionality | Not a working day | Implement 'drop bid' and 'drop section' functionality with jm | Write test cases for add bid functionality with jm | Not a working day | Not a working day
| Do you have any obstacles? | None | None | None | None | None | None | None

## Week 9
Person | Question | Week: 14/10/2019 to 20/10/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Xin Rong, Steffi | What did you do yesterday? | Not a working day | Completed remaining validations for boostrap with jm | Tested and debugged bootstrap with hs | Helped with scheduling, wrote test cases for 'open / close' round functionality | Received feedback from Online Review. Ammended scheduling. | Not a working day | Not a working day
| What will you do today? | Complete the remaining validations for bootstrap with jm | Test and debug bootstrap with hs | Helped with scheduling | Debug process_dropbid.php, help with presentation slides, Online Review | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | None | None | None | None | None | None | None
Lim Jie Min | What did you do yesterday? | Not a working day | Wrote test cases for bootstrap | Not a working day | Not a working day | Received feedback from Online Review. Ammended scheduling. | Not a working day | Not a working day
| What will you work on today? | Write test cases for bootstrap | Not a working day | Not a working day | Online Review | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | None | None | None | None | None | None | None
Lim Hui Sin | What did you do yesterday? | Adjusting schedule, daily updates | Adjusting schedule, daily updates | Adjusting schedule, daily updates, tested and debugged bootstrap with steffi, wrote test cases for 'drop bid' functionality with sky, tested and debugged 'drop bid' functionality with sky | Adjusting schedule, daily updates, worked on slides | Received feedback from Online Review. Ammended scheduling. Handover PM duties to Hilya | Not a working day | Not a working day
| What will you work on today? | Continue updating the schedule, daily updates | Continue updating the schedule, daily updates, test and debug bootstrap with steffi, write test cases for 'drop bid' and 'drop section' functionality, test and debug 'drop bid' and 'drop section' functionality with sky | Continue updating the schedule, daily updates, work on slides, deploy app on AWS | Continue updating the schedule, daily updates, work on slides, deploy app on AWS | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | None | None | None | None | None | None | None
Ku Seoung Lim (Sky) | What did you do yesterday? | Not a working day | Not a working day | Wrote test cases for 'drop bid' with hs, tested and debugged 'drop bid' functionality with hs | Debugged bootstrap and run through the test cases, completed 'open / close' round functionality with hilya | Received feedback from Online Review. Ammended scheduling. | Not a working day | Not a working day
| What will you work on today? | Not a working day | Test and debug 'drop bid' and 'drop section' functionality with hs | Debug bootstrap and run through the whole test cases with hilya | Online Review | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | None | None | None | None | None | None | None
Hilya Syazwani Binte Mohamed Yusoff | What did you do yesterday? | Not a working day | Not a working day | Worked on 'drop section' functionality | Debugged bootstrap and run through the test cases, completed 'open / close' round functionality with sky | Received feedback from Online Review. Ammended scheduling. Received all the updates and tasks as PM from Hui Sin | Updated schedule | Not a working day
| What will you work on today? | Not a working day | Work on 'drop section' functionality | Debug bootstrap and run through the whole test cases with hilya | Online Review | Update schedule. | Not a working day | Not a working day
| Do you have any obstacles? | None | None | None | None | None | None | None

## Week 10
Person | Question | Week: 21/10/2019 to 27/10/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Xin Rong, Steffi | What did you do yesterday? | Not a working day | Not a working day | Completed clearing round 1 logic | Planning the UI | Implemented round 2 realtime bidding results and redesigned placebid.php | Not a working day | Completed round 2 clearing logic
| What will you do today? | Not a working day | Start on clearing round 1 logic | Start on clearing round 2 logic (pt 1) | Implement round 2 clearing logic (pt1) | Continue to complete round 2 clearing logic | Continue to complete round 2 clearing logic | Help with JSON
| Do you have any obstacles? | None | None | None | None | None | None | None
Lim Jie Min | What did you do yesterday? | Not a working day | Not a working day | Completed clearing round 1 logic | Planning the UI | Implemented round 2 realtime bidding results and redesigned placebid.php | Not a working day | Completed round 2 clearing logic
| What will you work on today? | Not a working day | Start on clearing round 1 logic | Start on clearing round 2 logic (pt 1) | Implement round 2 clearing logic (pt1) | Continue to complete round 2 clearing logic | Continue to complete round 2 clearing logic | Help with JSON
| Do you have any obstacles? | None | Jie Min was struggling coding | None | None | None | None | None
Lim Hui Sin | What did you do yesterday? | Not a working day | Not a working day | Started on JSON API authentication | did authenticate, start and stop round for JSON | Redesigned authenticate to exclude token validation, start and stop to include token validation | Not a working day | Completed update_bid for JSON and has started on delete_bid for JSON
| What will you work on today? | Not a working day | Start on JSON API authentication | Continue JSON API authentication | Implement dump table for JSON and start on bootstrap for web service | Continue to implement dump table for JSON and start on bootstrap for web service | Start on update bid and delete bid for JSON | Continue to implement dump table for JSON and start on bootstrap for web service
| Do you have any obstacles? | None | None | None | None | None | None | None
Ku Seoung Lim (Sky) | What did you do yesterday? | Not a working day | Not a working day | Started on JSON API authentication | did authenticate, start and stop round for JSON | Redesigned authenticate to exclude token validation, start and stop to include token validation. Also created testcases. | Not a working day | Completed update_bid for JSON and has started on delete_bid for JSON
| What will you work on today? | Not a working day | Start on JSON API authentication | Continue JSON API authentication | Implement dump table for JSON and start on bootstrap for web service | Continue to implement dump table for JSON and start on bootstrap for web service | Start on update bid and delete bid for JSON | Continue to implement dump table for JSON and start on bootstrap for web service
| Do you have any obstacles? | None | Sky was struggling with coding | None | None | None | None | None
Hilya Syazwani Binte Mohamed Yusoff | What did you do yesterday? | Not a working day | Updated the schedule and daily updates. Also updated dropbid and dropsection. | Updated the schedule and daily updates. Also edited clearing round 1 logic. | Updated the schedule and daily updates. Started on creating other test cases | Updated the schedule and daily updates. Started on creating other test cases. Also created table for admin_index to show results after rounds have closed. | Continue updating the schedule, daily updates. Created testcase to test results table on admin_index.php | Updated the schedule, daily updates.
| What will you work on today? | Continue updating the schedule, daily updates | Continue updating the schedule, daily updates, and start on JSON API authentication | Continue updating the schedule, daily updates, and monitor JSON API authentication | Continue updating the schedule, daily updates. | Continue updating the schedule, daily updates. | Continue updating the schedule, daily updates. | Continue updating the schedule, daily updates.
| Do you have any obstacles? | None | Had to switch pairs for PP (Steffi and Jie Min, Hui Sin and Sky) | None | None | None | None | None

## Week 11
Person | Question | Week: 28/10/2019 to 03/11/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Xin Rong, Steffi | What did you do yesterday? | Replaced round1_clearing with process_bids. Completed round 1 and round 2 bidding and clearing logic | Updated data.sql and debugged JSON | Tested and debugged | updated sql script, tested and debugged | Debugging and deployment | Not a working day | Not a working day
| What will you do today? | Test cases for JSON | Test and debug authentication, start and stop round | Create dump table | Debugging and deployment | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | None | None | None | None | None | None | None
Lim Jie Min | What did you do yesterday? | Replaced round1_clearing with process_bids. Completed round 1 and round 2 bidding and clearing logic | Created testcases for dump_table JSON | Created test cases and debugged | updated sql script, tested and debugged. Created bootstrap test case files | Debugging with Steffi | Update the schedule and daily updates | Update the schedule and daily updates
| What will you work on today? | Test cases for JSON | Test cases for JSON and Test and debug authentication, start and stop round | Create dump table | Debugging and deployment | Update the schedule and daily updates | Update the schedule and daily updates | Update the schedule and daily updates
| Do you have any obstacles? | None | None | None | None | None | None | None
Lim Hui Sin | What did you do yesterday? | Completed drop_section. Edited update_bid and delete_bid | Not a working day | Test and debug round clearing logic | Not a working day | Not a working day | Not a working day | Not a working day
| What will you work on today? | Start on Dump table | Test and debug round clearing logic | Not a working day | Not a working day | Not a working day (on MC) | Not a working day (on MC) | Not a working day (on MC)
| Do you have any obstacles? | None | None | None | None | None | None | None
Ku Seoung Lim (Sky) | What did you do yesterday? | Completed drop_section. Edited update_bid and delete_bid | Started on user_dump | Completed user_dump and created test cases and edited bug metrics | Test and debugged round 2 logic. Updated process_placebid/BidDAO/update-bid/bid-dump/user-dump | Debugging, updated bug metrics | Not a working day | Not a working day
| What will you work on today? | Start on Dump table | Complete user_dump and create test cases for Round 2 logic | Continue to run tests and debug | Debugging and deployment | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | None | None | None | None | None | None | None
Hilya Syazwani Binte Mohamed Yusoff | What did you do yesterday? | Updated the schedule, daily updates. | Started on user_dump and completed section_dump | Updated the schedule, daily updates. | Continue updating the schedule, daily updates. Test and debugged round 2 logic. Updated process_placebid/BidDAO/update-bid/bid-dump/user-dump | Updated the schedule, daily updates. Debugging and deployment. | Not a working day | Not a working day
| What will you work on today? | Continue updating the schedule, daily updates. Help with other JSON API. | Continue updating the schedule, daily updates. | Continue updating the schedule, daily updates. Create bid status. Start on deployment. | Continue updating the schedule, daily updates. Debugging and start on deployment. | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | None | None | None | None | None | None | None

## Week 12
Person | Question | Week: 04/11/2019 to 10/11/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Xin Rong, Steffi | What did you do yesterday? | Not a working day | Debugging problems discovered in UAT (vacancies, e-Balance, min-bid amount) | Not a working day | Not a working day | Debugging problems discovered in UAT (vacancies, e-Balance, min-bid amount) | Not a working day | Not a working day
| What will you do today? | Debugging problems discovered in UAT (vacancies, e-Balance, min-bid amount) | Not a working day | Not a working day | Continue debugging problems discovered in UAT (vacancies, e-Balance, min-bid amount) | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | None | None | None | None | None | None | None
Lim Jie Min | What did you do yesterday? | Update the schedule and daily updates | Update the schedule and daily updates; debugging, editing UI with Hilya, testing JSON | Update the schedule and daily updates, debugging with Hilya | Update the schedule and daily updates | Update the schedule and daily updates | Update the schedule and daily updates | Update the schedule and daily updates
| What will you work on today? | Update the schedule and daily updates; debugging, editing UI with Hilya | Update the schedule and daily updates, debugging with Hilya | Update the schedule and daily updates, continue debugging with Hilya | Update the schedule and daily updates | Update the schedule and daily updates | Update the schedule and daily updates | Update the schedule and daily updates
| Do you have any obstacles? | None | None | None | None | None | None | None
Lim Hui Sin | What did you do yesterday? | Not a working day | Not a working day | Write testcases for JSON authenticate | Not a working day | Not a working day | Write testcases for JSON bootstrap | Not a working day
| What will you work on today? | Not a working day (on MC) | Write testcases for JSON | Not a working day | Not a working day | Write testcases for JSON bootstrap | Not a working day | Not a working day
| Do you have any obstacles? | None | None | None | None | None | None | None
Ku Seoung Lim (Sky) | What did you do yesterday? | Not a working day | Debugging problems discovered in UAT (vacancies, e-Balance, min-bid amount), testing JSON | Not a working day | Not a working day | Debugging of app | Write testcases for JSON | Not a working day
| What will you work on today? | Debugging problems discovered in UAT (vacancies, e-Balance, min-bid amount) | Not a working day | Not a working day | Work on debugging bid clearing functions with Steffi | Write testcases for JSON | Not a working day | Not a working day
| Do you have any obstacles? | None | None | None | None | None | None | None
Hilya Syazwani Binte Mohamed Yusoff | What did you do yesterday? | Not a working day | Debugging and editting the UI with reference to UAT feedback | Debugging bid status | Debugging and editting the UI e.g., for admin login, error messages | Not a working day | Write testcases for JSON | Not a working day
| What will you work on today? | Debugging and editting the UI with reference to UAT feedback | Debugging bid status | Continue debugging bid processing functions | Not a working day | Write testcases for JSON | Not a working day | Not a working day
| Do you have any obstacles? | None | None | None | None | None | None | None

## Week 13
Person | Question | Week: 11/11/2019 to 17/11/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Xin Rong, Steffi | What did you do yesterday?
What will you do today?
Do you have any obstacles?
Lim Jie Min | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Lim Hui Sin | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Ku Seoung Lim (Sky) | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Hilya Syazwani Binte Mohamed Yusoff | What did you do yesterday?
What will you work on today?
Do you have any obstacles?