## Week 5
Person | Question | Week: 16/09/2019 to 22/09/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Xin Rong, Steffi | What did you do yesterday? |  |  |  |  | Met and discussed the schedule and assigned roles for this iteration | Edited schedule | Edited schedule
| What will you do today? |  |  |  |  | Continue updating the schedule | Continue updating the schedule | Continue updating the schedule
| Do you have any obstacles? |  |  |  |  | None | None | None
Lim Jie Min | What did you do yesterday? |  |  |  |  | Planned schedule with the team | Not a working day | Not a working day
| What will you work on today? |  |  |  |  | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? |  |  |  |  | NA | NA | NA
Lim Hui Sin | What did you do yesterday? |  |  |  |  | Met with team to plan schedule | Not a working day | Not a working day
| What will you work on today? |  |  |  |  | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? |  |  |  |  | NA | NA | NA
Ku Seoung Lim | What did you do yesterday? |  |  |  |  | Team meeting | Not a working day | Not a working day
| What will you work on today? |  |  |  |  | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? |  |  |  |  | NA | NA | NA
Hilya Syazwani Binte Mohamed Yusoff | What did you do yesterday? |  |  |  |  | Attended meeting to discuss schedule, committed and pushed the minutes to repo | Not a working day | Not a working day
| What will you work on today? |  |  |  |  | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? |  |  |  |  | NA | NA | NA

## Week 6
Person | Question | Week: 23/09/2019 to 29/09/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Xin Rong, Steffi | What did you do yesterday? | Edited schedule, daily updates | Edited schedule, daily updates, team meeting | Edited schedule, daily updates | Edited schedule, daily updates | Edited schedule, daily updates | Edited schedule, daily updates | Edited schedule, daily updates
| What will you do today? | Edit schedule, daily updates, team meeting | Edit schedule, daily updates | Continue updating the schedule, daily updates | Continue updating the schedule, daily updates | Continue updating the schedule, daily updates | Continue updating the schedule, daily updates | Continue updating the schedule, daily updates
| Do you have any obstacles? | None | None | None | None | None | None | None
Lim Jie Min | What did you do yesterday? | Not a working day | Coded login page | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| What will you work on today? | Team meeting, PP for login page | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | None | NA | NA | NA | NA | NA | NA
Lim Hui Sin | What did you do yesterday? | Not a working day | Created SQL database, coded classes and DAOs, created bootstrap.php | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| What will you work on today? | Team meeting, PP for login page | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | None | NA | NA | NA | NA | NA | NA
Ku Seoung Lim | What did you do yesterday? | Not a working day | Created SQL database, coded classes and DAOs, created bootstrap.php | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| What will you work on today? | Team meeting, PP for bootstrap | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | None | NA | NA | NA | NA | NA | NA
Hilya Syazwani Binte Mohamed Yusoff | What did you do yesterday? | Not a working day | Coded login page | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| What will you work on today? | Team meeting, PP for bootstrap | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | None | NA | NA | NA | NA | NA | NA

## Week 7
Person | Question | Week: 30/09/2019 to 06/10/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Xin Rong, Steffi | What did you do yesterday? | Edited schedule, daily updates | Edited schedule, daily updates | Overhauled the schedule and planned until the end of the project, held team meeting to ensure everyone is on the same page. Daily update | Finalised schedule, worked on slides | Deployed app, submitted slides and did PM Review | Helped with adjusting schedule | Helped with scheduling, fixed admin login
| What will you do today? | Prepare PM Review slides, Update schedule, daily updates | Team meeting, update schedule until end of project, daily updates | Simplify tasks on schedule as there is too much detail. Will draw critical path and prepare slides for PM review | Deploy app, submit slides, PM Review | Revisit scheduling | Help with scheduling, fix admin login | Not a working day
| Do you have any obstacles? | None | None | None | I haven’t tried deploying the app before, so hopefully there are no delays | None | None | None
Lim Jie Min | What did you do yesterday? | Not a working day | Finished all bootstrap validations up to course_completed | Attended the team meeting, helped to write the login test cases and updated the bug metrics | Added more DAO functions and implemented login for admin | Attended PM Review | Not a working day | Not a working day
| What will you work on today? | Complete bootstrap.php validations | Team meeting, write test cases for login, add to bug metrics | Add more DAO functions and add the login page for admin. | PM Review | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | None | None | None | None | None | None | None
Lim Hui Sin | What did you do yesterday? | Not a working day | Finished all bootstrap validations up to course_completed | I went for the team meeting, ran the test cases to test login and debugged the code. | Updated the DAOs and finished login for the admin | Helped with slides and PM Review | Adjusting schedule, daily updates | Adjusting schedule, daily updates
| What will you work on today? | Continue and finish coding bootstrap.php and bootstrapping validations | Team meeting, test login functionality, debugging | Implement more methods in our DAOs and code the login functionality for the admin. | I'll help with the slides and attend the PM Review | Revisit scheduling | Revisit schedule, daily updates | Continue updating the schedule, daily updates
| Do you have any obstacles? | None | None | None | None | None | None | None
Ku Seoung Lim | What did you do yesterday? | Not a working day | Created bidding results summary table for student home page, began coding 'plan bid' page | Attended team meeting. Clarify project requirements I wasn't sure about. Also helped to test login and debug the code. | Not a working day | Drew critical paths for the slides, attended PM Review | Not a working day | Fixed admin login
| What will you work on today? | Update student login landing page, coding bootstrap form for admin page | Team meeting, test login functionality, debugging | Not a working day | I will draw the critical paths for the slides, PM review | Not a working day | Fix admin login | Not a working day
| Do you have any obstacles? | None | None | None | None | None | None | None
Hilya Syazwani Binte Mohamed Yusoff | What did you do yesterday? | Not a working day | Created bidding results summary table for student home page, started on 'plan bid' page | Not a working day | Not a working day | Attended PM Review | Not a working day | Not a working day
| What will you work on today? | Creating bidding summary table for studen'ts landing page, creating admin's page for bootstrapping | Not a working day | Not a working day | PM Review | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | None | None | None | None | None | None | None

## Week 8
Person | Question | Week: 07/10/2019 to 13/10/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Xin Rong, Steffi | What did you do yesterday?
What will you do today?
Do you have any obstacles?
Lim Jie Min | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Lim Hui Sin | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Ku Seoung Lim | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Hilya Syazwani Binte Mohamed Yusoff | What did you do yesterday?
What will you work on today?
Do you have any obstacles?

## Week 9
Person | Question | Week: 14/10/2019 to 20/10/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Xin Rong, Steffi | What did you do yesterday?
What will you do today?
Do you have any obstacles?
Lim Jie Min | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Lim Hui Sin | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Ku Seoung Lim | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Hilya Syazwani Binte Mohamed Yusoff | What did you do yesterday?
What will you work on today?
Do you have any obstacles?

## Week 10
Person | Question | Week: 21/10/2019 to 27/10/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Xin Rong, Steffi | What did you do yesterday?
What will you do today?
Do you have any obstacles?
Lim Jie Min | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Lim Hui Sin | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Ku Seoung Lim | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Hilya Syazwani Binte Mohamed Yusoff | What did you do yesterday?
What will you work on today?
Do you have any obstacles?

## Week 11
Person | Question | Week: 28/10/2019 to 03/11/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Xin Rong, Steffi | What did you do yesterday?
What will you do today?
Do you have any obstacles?
Lim Jie Min | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Lim Hui Sin | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Ku Seoung Lim | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Hilya Syazwani Binte Mohamed Yusoff | What did you do yesterday?
What will you work on today?
Do you have any obstacles?

## Week 12
Person | Question | Week: 04/11/2019 to 10/11/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Xin Rong, Steffi | What did you do yesterday?
What will you do today?
Do you have any obstacles?
Lim Jie Min | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Lim Hui Sin | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Ku Seoung Lim | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Hilya Syazwani Binte Mohamed Yusoff | What did you do yesterday?
What will you work on today?
Do you have any obstacles?

## Week 13
Person | Question | Week: 11/11/2019 to 17/11/2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Tan Xin Rong, Steffi | What did you do yesterday?
What will you do today?
Do you have any obstacles?
Lim Jie Min | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Lim Hui Sin | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Ku Seoung Lim | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Hilya Syazwani Binte Mohamed Yusoff | What did you do yesterday?
What will you work on today?
Do you have any obstacles?