## Instructions
Severity | Description
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
Points in Iteration | Action
Points < 10 | Use the planned debugging time in the iteration.
Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.

## Bug Metrics
Bug Metrics
S/N | Iteration | Function | Description | Severity | Points | Final Bug Metric (Points Total) | Mitgation
1 | 1 | Login (Student) | Successful login brought the user to 'Plan Bid' page instead of the student home page | High | 5 | 41 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
2 | 1 | Login (Student) | User name displayed on home page did not change according to the user that logged in | Low | 1
3 | 1 | Login (Admin) | Admin got directed to student home page instead of bidding admin page and hence causing error and causes login to be unsuccessful | High | 5
4 | 1 | Login (Admin) | Admin is able to login successfully when they key in their password in caps | High | 5
5 | 1 | Login (Student) | Student is able to login successfully when they select their role as admin and was brought to the bidding admin page | Critical | 10
6 | 2.1 | Add Bid | Your bid was placed successfully!' was displayed instead of the expected error message when student enters non-existing course code | High | 5 |  | Use the planned debugging time in the iteration.
7 | 2.1 | Add Bid | Student was able to bid for course that are not offered by their school during round 1 | High | 5
8 | 2.1 | Add Bid | Student was able to bid for courses where they have not fulfilled the necessary pre-requisite course(s) | High | 5
9 | 2.2 | Bootstrap | SQL error: Tables could not be truncated due to foreign key constraints | Critical | 10 | 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
10 | 2.2 | Bootstrap | Incorrect variable name | Critical | 10 | 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
11 | 2.2 | Bootstrap | Error due to calling class methods inside a PDO function | Critical | 10 | 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
12 | 2.2 | Bootstrap | Too few arguments in 'validateDate()' | Critical | 10 | 10
13 | 2.2 | Bootstrap | SQL error: Column not found (used wrong column name) | Critical | 10 | 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
14 | 2.2 | Bootstrap | Issue with the validateDate() function in common.php, causing all exam dates to be invalid | High | 5 | 11 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
15 | 2.2 | Bootstrap | Incorrect row numbers shown in bootstrap errors | Low | 1
16 | 2.3 | Drop Bid | Cannot access private property Student::$edollar | High | 5
17 | 2.3 | Drop Bid | After dropping bid, updated e$ amount is not displayed | Low | 1 | 11 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
18 | 2.2 | Bootstrap | Undefined variable: getCourse | Critical | 10
19 | 2.2 | Bootstrap | Call to undefined method Prerequisite::getUserid() in CourseCompletedDAO.php | Critical | 10 | 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
20 | 2.2 | Bootstrap | Too few arguments for function $sectionDAO->retrieve() on line 538 | Critical | 10 | 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
21 | 2.2 | Bootstrap | Undefined variable: alreadyBidded | Critical | 10 | 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
22 | 2.2 | Bootstrap | SQL error: Failed to update due to the use of wrong variable name | Critical | 10 | 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
23 | 2.2 | Bootstrap | SQL error: duplicate entry due to incorrect validations against bid for same section | Critical | 10 | 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
24 | 2.2 | Bootstrap | Edollar balance not updated in database | High | 5 | 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
25 | 2.2 | Bootstrap | Edollar balance not updated in database | High | 5
26 | 2.2 | Bootstrap | Bootstrap succesful but error are not reported when the pre-requisite course has yet to be attempted | Low | 1
27 | 2.2 | Bootstrap | Bootstrap successful but error not displayed when amount in bidded is less than e$10 | Low | 1
28 | 2.2 | Bootstrap | Bootstrap unsuccessful and bid has entered the database when the amount in bid is less than e$10 | High | 5
29 | 2.2 | Bootstrap | No error displayed for when student is unable to place bids when there is insufficient e$ | Low | 1
30 | 2.2 | Bootstrap | Bootstrap unsuccessful due to incorrect data input in the bootstrap folder | Low | 1
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198

## Bug Log
Bug Log
S/N | Iteration | Function | Description | Status | Discovered On | Resolved On | Fixed by (PP Team)
1 | 1 | Login (Student) | Successful login brought the user to 'Plan Bid' page instead of the student home page | Resolved | 2017-10-01 | 2017-10-01 | HS & SL
2 | 1 | Login (Student) | User name displayed on home page did not change according to the user that logged in | Resolved | 2017-10-01 | 2017-10-01 | HS & SL
3 | 1 | Login (Admin) | Admin got directed to student home page instead of bidding admin page and hence causing error and causes login to be unsuccessful | Resolved | 2017-10-01 | 2017-10-01 | HS & SL
4 | 1 | Login (Admin) | Admin is able to login successfully when they key in their password in caps | Resolved | 2017-10-01 |  | HS & SL
5 | 1 | Login (Student) | Student is able to login successfully when they select their role as admin and was brought to the bidding admin page | Resolved | 2017-10-01 | 2017-10-01 | HS & SL
6 | 2.1 | Add Bid | Your bid was placed successfully!' was displayed instead of the expected error message when student enters non-existing course code | Resolved | 2017-10-01 | 2017-10-04 | JM & ST
7 | 2.1 | Add Bid | Student was able to bid for course that are not offered by their school during round 1 | Resolved | 2017-10-04 | 2017-10-05 | JM & ST
8 | 2.1 | Add Bid | Student was able to bid for courses where they have not fulfilled the necessary pre-requisite course(s) | Resolved | 2017-10-05 | 13/10/2017 | JM & ST
9 | 2.2 | Bootstrap | SQL error: Tables could not be truncated due to foreign key constraints | Resolved | 2019-10-15 | 2019-10-15 | HS & ST
9 | 2.2 | Bootstrap | Incorrect variable name | Resolved | 2019-10-15 | 2019-10-15 | HS & ST
10 | 2.2 | Bootstrap | Error due to calling class methods inside a PDO function | Resolved | 2019-10-15 | 2019-10-15 | HS & ST
11 | 2.2 | Bootstrap | Too few arguments in 'validateDate()' | Resolved | 2019-10-15 | 2019-10-15 | HS & ST
13 | 2.2 | Bootstrap | SQL error: Column not found (used wrong column name) | Resolved | 2019-10-15 | 2019-10-15 | HS & ST
14 | 2.2 | Bootstrap | Issue with the validateDate() function in common.php, causing all exam dates to be invalid | Resolved | 2019-10-15 | 2019-10-15 | HS & ST
15 | 2.2 | Bootstrap | Incorrect row numbers shown in bootstrap errors | Resolved | 2019-10-15 | 2019-10-15 | HS & ST
16 | 2.3 | Drop Bid | Cannot access private property Student::$edollar | Resolved | 2019-10-15 | 2019-10-15 | HS & SL
17 | 2.3 | Drop Bid | After dropping bid, updated e$ amount is not displayed | Resolved | 2019-10-15 | 2019-10-16 | SL & HY
18 | 2.2 | Bootstrap | Undefined variable: getCourse | Resolved | 2019-10-16 | 2019-10-16 | SL & HY
19 | 2.2 | Bootstrap | Call to undefined method Prerequisite::getUserid() in CourseCompletedDAO.php | Resolved | 2019-10-16 | 2019-10-16 | SL & HY
20 | 2.2 | Bootstrap | Too few arguments for function $sectionDAO->retrieve() on line 538 | Resolved | 2019-10-16 | 2019-10-16 | SL & HY
21 | 2.2 | Bootstrap | Undefined variable: alreadyBidded | Resolved | 2019-10-16 | 2019-10-16 | SL & HY
| 2.2 | Bootstrap | SQL error: Failed to update due to the use of wrong variable name | Resolved | 2019-10-16 | 2019-10-16 | SL & HY
| 2.2 | Bootstrap | SQL error: duplicate entry due to incorrect validations against bid for same section | Resolved | 2019-10-16 | 2019-10-16 | SL & HY
| 2.2 | Bootstrap | Edollar balance not updated in database | Resolved | 2019-10-16 | 2019-10-16 | SL & HY
| 2.2 | Bootstrap | Edollar balance not updated in database | Resolved | 2019-10-16 | 2019-10-16 | SL & HY
| 2.2 | Bootstrap | Errors are not reported when the pre-requisite course has yet to be attempted | Resolved | 2019-10-16 | 2019-10-16 | SL & HY
| 2.2 | Bootstrap | Bootstrap successful but error not displayed when amount in bidded is less than e$10 | Unresolved | 2019-10-16 |  | SL & HY
| 2.2 | Bootstrap | Bootstrap unsuccessful and bid has entered the database when the amount in bid is less than e$10 | Unresolved | 2019-10-16 |  | SL & HY
| 2.2 | Bootstrap | No error displyed for when student is unable to place bids when there is insufficient e$ | Unresolved | 2019-10-16 |  | SL & HY
| 2.2 | Bootstrap | Bootstrap unsuccessful due to incorrect data input in the bootstrap folder | Unresolved | 2019-10-16 |  | SL & HY
Unresolved
Unresolved
Unresolved
Unresolved
Unresolved
Unresolved
Unresolved