## Sheet1
S/N | Functionality | Description | Test Inputs | Test Procedure | Expected Results | Actual Results 1 | Actual Results 2 | Actual Results 3 | Actual Results 4 | Actual Results 5 | Actual Results 6 | Actual Results 7
1 | 1.1 | Validate that student with correct credentials can login | Username: amy.ng.2009 Password: qwerty128 | Select student as their role, put username into username input field, put password into password input field. Submit | Login success, student home page displayed with correct bidding summary | Login successful but redirected to 'plan bid' instead of 'home' page | Login successful but wrong name was displayed on home page | Login successful, bidding summary matches expected result | 17/10/2019 Iter 2 Regression Testing Matched expected results
2 | 1.1 | Validate that student who did not key in username would not be able to login successfully and show error message | Username: Password: qwerty128 | Select student as their role, do not key in anything in the username input field, put password into password input field. Submit | Login failed, show error message | Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
3 | 1.1 | Validate that student who did not key in password would not be able to login successfully and show error message | Username: amy.ng.2009 Password: | Select student as their role, put username into username input field, do not key in anything in the password input field. Submit | Login failed, show error message | Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
4 | 1.1 | Validate that student with incorrect username would not be able to login and show error message | Username: amy.ng Password: qwerty128 | Select student as their role, put username into username input field, put password into password input field. Submit | Login failed, show error message | Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
5 | 1.1 | Validate that student with incorrect password would not be able to login and show error message | Username: amy.ng.2009 Password: 123456 | Select student as their role, put username into username input field, put password into password input field. Submit | Login failed, show error message | Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
6 | 1.1 | Validate that admin with correct credentials can login | Username: admin Password: adminpassword | Select admin as their role, put username into username input field, put password into password input field. Submit | Login success, bidding details for admin is displayed. | Login unsuccessful and error displayed (got directed to student home page and hence causing error as admin do not have correct bidding summary) | Login successful, bidding admin page matches expected result | 17/10/2019 Iter 2 Regression Testing Matched expected results
7 | 1.1 | Validate that if admin did not key in username, they would not be able to login successfully and show error message | Username: Password: adminpassword | Select admin as their role, do not key in anything in the username input field, put password into password input field. Submit | Login failed, show error message | Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
8 | 1.1 | Validate that if admin did not key in password, they would not be able to login successfully and show error message | Username: admin Password: | Select admin as their role, put username into username input field, do not key in anything in the password input field. Submit | Login failed, show error message | Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
9 | 1.1 | Validate that admin with incorrect username would not be able to login and show error message | Username: admin123 Password: password | Select admin as their role, put username into username input field, put password into password input field. Submit | Login failed, show error message | Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
10 | 1.1 | Validate that admin with incorrect password would not be able to login and show error message | Username: admin Password: woshiadmin | Select admin as their role, put username into username input field, put password into password input field. Submit | Login failed, show error message | Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
11 | 1.1 | Ensure that admin would not be able to login if they key in their password in CAPS | Username: admin Password: ADMINPASSWORD | Select admin as their role, put username into username input field, key in password in CAPS into password input field. Submit | Login failed, show error message | Login successful and was brought to the bidding admin page | Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
12 | 1.1 | OBSOLETE TEST CASE Validate if student is able to login into admin home page using student's credentials | Username: amy.ng.2009 Password: qwerty128 | Select student as their role, put username into username input field, put password into password input field. Submit | Login failed, show error message | Login successful and was brought to the bidding admin page | Matched expected results
13 | 2.1 | Validate that in bidding round 1, a student can successfully place a bid by entering an existing course code, section number, and e$ >= 10 where the course is offered by the student’s school and does not have prerequisite courses and there are no class/exam timetables clashes and student has not already bidded for 5 sections and student has not bidded for any other section in the same course | Bidding round 1: open Username: amy.ng.2009 Password: qwerty128 Course Code: IS205 Section Number: S1 E-dollars: 10 Username: parker.ng.2009 Password: qwerty143 Course Code: ECON001 Section Number: S1 E-dollars: 19 Username: winston.ng.2009 Password: qwerty150 Course Code: MGMT002 Section Number: S1 E-dollars: 12 | Student enters existing course code, existing section number and e$ >= 10. Place Bid. | Bid successfully placed | 11/10/2019 Matched expected results | 11/10/2019 Matched expected results | 11/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
14 | 2.1 | Validate that in bidding round 1, a student can successfully place a bid by entering an existing course code, section number, and e$ >= 10 where the course is offered by the student’s school, and the student has taken all the necessary prerequisite courses, and there are no class/exam timetables clashes and student has not already bidded for 5 sections and student has not bidded for any other section in the same course | Bidding round 1: open Username: amy.ng.2009 Password: qwerty128 Course Code: IS101 Section Number: S1 E-dollars: 10 Username: ben.ng.2009 Password: qwerty129 Course Code: IS203 Section Number: S1 E-dollars: 10 | Student enters existing course code, existing section number and e$ >= 10. Place Bid. | Bid successfully placed | 11/10/2019 Matched expected results | 11/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
15 | 2.1 | Validate that student is unable to place bids when course code is missing | Bidding round 1: open Username: amy.ng.2009 Password: qwerty128 Course Code: Section Number: S1 E-dollars: 10 | Student enters existing section number and e$ >= 10, but does not enter course code. Place Bid. | Place bid fail, show error message | 11/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
16 | 2.1 | Validate that student is unable to place bids when section number is missing | Bidding round 1: open Username: amy.ng.2009 Password: qwerty128 Course Code: IS205 Section Number: E-dollars: 10 | Student enters existing course code and e$ >= 10, but does not enter section number. Place Bid. | Place bid fail, show error message | 11/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
17 | 2.1 | Validate that student is unable to place bids when e$ amound is missing | Bidding round 1: open Username: amy.ng.2009 Password: qwerty128 Course Code: IS205 Section Number: S1 E-dollars: | Student enters existing course code and section number, but does not enter e$ amount. Place Bid. | Place bid fail, show error message | 11/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
18 | 2.1 | Validate that student is unable to place bids when e$ amound < 10 | Bidding round 1: open Username: amy.ng.2009 Password: qwerty128 Course Code: IS205 Section Number: S1 E-dollars: 8 | Student enters existing course code and section number, but enters e$ amount < 10. Place Bid. | Place bid fail, show error message | 11/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
19 | 2.1 | Validate that student is unable to place bids where course code does not exist | Bidding round 1: open Username: amy.ng.2009 Password: qwerty128 Course Code: IS567 Section Number: S1 E-dollars: 10 | Student enters non-existing course code, random section number and e$ >= 10. Place Bid. | Place bid fail, show error message | 11/10/2019 Bid was placed successfully. | 11/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
20 | 2.1 | Validate that student is unable to place bids where section number does not exist | Bidding round 1: open Username: amy.ng.2009 Password: qwerty128 Course Code: IS205 Section Number: S11 E-dollars: 12 | Student enters existing course code, non-existing section number and e$ >= 10. Place Bid. | Place bid fail, show error message | 11/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
21 | 2.1 | Validate that in bidding round 1, student is unable to place bids where course is not offered by the student's school | Bidding round 1: open Username: amy.ng.2009 Password: qwerty128 Course Code: MGMT001 Section Number: S1 E-dollars: 10 | Student enters existing course code, existing section number and e$ >= 10, where course is offered by another school. Place Bid. | Place bid fail, show error message | 11/10/2019 Bid was placed successfully when student tried to bid courses that are not offered by their school | 11/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
22 | 2.1 | Validate that student is unable to place bids for more than 5 sections | Bidding round 1: open Username: ben.ng.2009 Password: qwerty129 Course Code 1: IS205 Section Number: S1 E-dollars: 10 Course Code 2: IS100 Section Number: S1 E-dollars: 10 Course Code 3: IS105 Section Number: S2 E-dollars: 10 Course Code 4: IS106 Section Number: S2 E-dollars: 10 Course Code 5: IS200 Section Number: S1 E-dollars: 10 Course Code 6: IS201 Section Number: S1 E-dollars: 10 | Student enters existing course code, existing section number and e$ >= 10 after successfully placing bids for 5 sections. Place Bid. | Place bid fail, show error message | 11/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
23 | 2.1 | Validate that student is unable to place bids for more than 1 section in the same course | Bidding round 1: open Username: amy.ng.2009 Password: qwerty128 Course Code: IS107 Section Number: S1 E-dollars: 10 Course Code 2: IS107 Section Number: S2 E-dollars: 10 | Student enters existing course code, existing section number and e$ >= 10 after placing bids for another section of the same course. Place Bid. | Place bid fail, show error message | 11/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
24 | 2.1 | Validate that student is unable to place bids when there is insufficient e$ | Bidding round 1: open Username: ben.ng.2009 Password: qwerty129 Course Code 1: IS205 Section Number: S1 E-dollars: 198 Course Code 2: IS100 Section Number: S1 E-dollars: 10 | Student enters existing course code, existing section number and e$ >= 10 even though e$ balance < 10. Place Bid. | Place bid fail, show error message | 11/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
25 | 2.1 | Validate that student is unable to place bids when class timetables clash | Bidding round 1: open Username: ben.ng.2009 Password: qwerty129 Course Code 1: IS205 Section Number: S1 E-dollars: 18 Course Code 2: IS105 Section Number: S1 E-dollars: 10 | Student enters existing course code, existing section number and e$ >= 10 for two courses with clashing class timings. Place Bid. | Place bid fail, show error message | 11/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
26 | 2.1 | Validate that student is unable to place bids when exam timetables clash | Bidding round 1: open Username: ben.ng.2009 Password: qwerty129 Course Code 1: IS205 Section Number: S1 E-dollars: 18 Course Code 2: 210 Section Number: S1 E-dollars: 21 | Student enters existing course code, existing section number and e$ >= 10 for two courses with clashing exam timings. Place Bid. | Place bid fail, show error message | 11/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
27 | 2.1 | Validate that student is unable to place bids for courses already completed | Bidding round 1: open Username: amy.ng.2009 Password: qwerty128 Course Code: IS100 Section Number: S1 E-dollars: 10 | Student enters existing course code, existing section number and e$ >= 10 for a course that the student had previously completed. Place Bid. | Place bid fail, show error message | 11/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
28 | 2.1 | Validate that student is unable to place bids for courses where student has not fulfilled the necessary pre-requisite course(s) | Bidding round 1: open Username: amy.ng.2009 Password: qwerty128 Course Code: IS103 Section Number: S1 E-dollars: 10 | Student enters existing course code, existing section number and e$ >= 10 for a course with a prerequisite the student has not completed. Place Bid. | Place bid fail, show error message | 11/10/2019 Bid was placed successfully when student tried to bid for a course that he/she has not fulfilled the necessary pre-requisite course | 11/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
29 | 2.1 | Testing bootstrap using provided sample data | SampleData-fixed.zip | Upload SampleData-fixed.zip on the boostrap page and press "Import" | Bootstrap succeeds. Data successfully added Error on course.csv row 6 ('course completed) and bid.csv rows 13 onwards ('not own school course') displayed correctly | 15/10/2019 Cannot truncate a table referenced in a foreign key constraint (`is212_spm_data`.`bid`, CONSTRAINT `bid_fk1` FOREIGN KEY (`userid`) | 15/10/2019 Undefined variable: userId Only variables should be passed by reference in StudentDAO.php Call to undefined method Student::getPwd() | 15/10/2019 Too few arguments to function validateDate(), 1 passed in bootstrap.php and exactly 2 expected | 15/10/2019 Column not found: Unknown column 'round_number' in line 32 of RoundDAO.php | 15/10/2019 course.csv - row 1 - invalid exam start / end All row numbers were '1', not showing correct row numbers All course rows were skipped due to invalid times --> all subsequent files could not be processed | 15/10/2019 Row numbers now correct but programme is still throwing errors for invalid exam start / end (course.csv) | 16/10/2019 Undefined variable: getCourse | 16/10/2019 Call to undefined method Prerequisite::getUserid() in CourseCompletedDAO.php | 16/10/2019 Too few arguments to function SectionDAO::retrieve(), 1 passed and exactly 2 expected on line 538 | 16/10/2019 Undefined variable: alreadyBidded | 16/10/2019 Cannot add or update a child row: a foreign key constraint fails (due to call to wrong variable) | 16/10/2019 Duplicate entry 'zac.ng.2009-MGMT001-S1' (no validations against bid for same section) | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
30 | 2.2 | Validate that there is no whitespace at the start or end of each field in student.csv | userid: dawn.ng.2009 password: qwerty131 name: Dawn NG school: SIS edollar: 200 userid: quiten.ng.2009 password: qwerty144 name: Quiten NG school: SOE edollar: 200 userid: ricky.ng.2009 password: qwerty145 name: Ricky NG school: SOE edollar: 200 userid: xavier.ng.2009 password: qwerty151 name: Xavier NG school: SOB edollar: 200 userid: calvin.ng.2009 password: qwerty130 name: Calvin NG school: SIS edollar: 200 | Upload test_whitespace_student_and_course.zip | Bootstrap succeeds, data added successfully. Values in database have no whitespace. | 16/10/2019 Cannot truncate a table referenced in a foreign key constraint (`is212_spm_data`.`bid`, CONSTRAINT `bid_fk1` FOREIGN KEY (`userid`) | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
31 | 2.2 | Validate that there is no whitespace at the start or end of each field in course.csv | course: IS101 school: SIS title: Advanced Calculus description: This is a second course on calculus. It is more advanced definitely. exam date: 20131118 exam start: 12:00 exam end: 15:15 course: IS102 school: SIS title: Java programming description: This course teaches you on Java programming. I love Java definitely. exam date: 20131117 exam start: 15:30 exam end: 18:45 course: IS107 school: SIS title: IT Outsourcing description: This course teaches you on how to outsource your programming projects to others. exam date: 20131112 exam start: 12:00 exam end: 15:15 course: IS200 school: SIS title: Final Touch description: Learn how eat, dress and talk. exam date: 20131109 exam start: 12:00 exam end: 15:15 course: IS205 school: SIS title: All Talk, No Action description: The easiest course of all. We will sit around and talk. exam date: 20131104 exam start: 8:30 exam end: 11:45 | Upload test_whitespace_student_and_course.zip | Bootstrap succeeds, data added successfully. Values in database have no whitespace. | 16/10/2019 Cannot truncate a table referenced in a foreign key constraint (`is212_spm_data`.`bid`, CONSTRAINT `bid_fk1` FOREIGN KEY (`userid`) | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
| 2.2 | Validate that there is no whitespace at the start or end of each field in section.csv | course: IS101 section: S1 day: 3 start: 15:30 end: 18:45 instructor: Cheri KHOO venue: Seminar Rm 2-3 size: 10 course: IS101 section: S2 day: 4 start: 8:30 end: 11:45 instructor: Daniel KHOO venue: Seminar Rm 2-4 size: 10 course: IS101 section: S3 day: 5 start: 12:00 end: 15:15 instructor: Ernest KHOO venue: Seminar Rm 2-5 size: 10 course: IS107 section: S1 day: 3 start: 15:30 end: 18:45 instructor: Ray KHOO venue: Seminar Rm 2-18 size: 10 course: IS107 section: S2 day: 4 start: 8:30 end: 11:45 instructor: Simon KHOO venue: Seminar Rm 2-19 size: 10 | Upload test_whitespace_section.zip | Bootstrap succeeds, data added successfully. Values in database have no whitespace. | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
| 2.2 | Validate that there is no whitespace at the start or end of each field in prerequisite.csv | course: IS101 prerequisite: IS100 course: IS103 prerequisite: IS102 course: IS203 prerequisite: IS106 | Upload test_whitespace_prerequisite.zip | Bootstrap succeeds, data added successfully. Values in database have no whitespace. | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
| 2.2 | Validate that there is no whitespace at the start or end of each field in course_completed.csv | userid: amy.ng.2009 code: IS100 userid: gary.ng.2009 code: IS100 | Upload test_whitespace_course_completed.zip | Bootstrap succeeds, data added successfully. Values in database have no whitespace. | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
| 2.2 | Validate that there is no whitespace at the start or end of each field in bid.csv | userid: dawn.ng.2009 amount: 22 code: IS205 section: S1 status: Pending userid: timothy.ng.2009 amount: 12 code: ECON001 section: S1 status: Pending userid: xavier.ng.2009 amount: 42 code: MGMT002 section: S1 status: Pending | Upload test_whitespace_bid.zip | Bootstrap succeeds, data added successfully. Values in database have no whitespace. | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
| 2.2 | Validate that student.csv has no blank fields: userid, password, name, school, edollar | userid: password: qwerty128 name: Amy NG school: SIS edollar: 200 userid: amy.ng.2009 password: name: Amy NG school: SIS edollar: 200 userid: amy.ng.2009 password: qwerty128 name: school: SIS edollar: 200 userid: amy.ng.2009 password: qwerty128 name: Amy NG school: edollar: 200 userid: amy.ng.2009 password: qwerty128 name: Amy NG school: SIS edollar: userid: password: name: school: edollar: | Copy the given Test Inputs into student.csv (bootstrap data file) for each scenario. Run localhost/project-g1t8/app/bootstrap, Choose File: student.csv. Import | Show error message "blank [field]" for each blank field, and output in the left-to-right order of the CSV fields | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
32 | 2.2 | Validate that the userid field in student.csv must not exceed 128 characters. | userid: amy.ng.20091234567890abcdefghijklmnopqrstuvwxyzabcdefghijklmnopqrstuvwxyzabcdefghijklmnopqrstuvwxyzabcdefghijklmnopqrstuvwxyzabcdefghijklmnopqrstuvwxyzabcdefghijklmnopqrstuvwxyzabcdefghijklmnopqrstuvwxyzabcdefghijklmnopqrstuvwxyz password: qwerty128 name: Amy NG school: SIS edollar: 200 | Copy the given Test Inputs into student.csv (bootstrap data file) with userid > 128 characters. Run localhost/project-g1t8/app/bootstrap, Choose File: student.csv. Import | Show error message "invalid userid" | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
33 | 2.2 | Validate that there is no existing user with the same userid in student.csv | userid: amy.ng.2009 password: qwerty128 name: Amy NG school: SIS edollar: 200 userid: amy.ng.2009 password: qwerty129 name: Ben NG school: SIS edollar: 200 | Copy the given Test Inputs into student.csv (bootstrap data file) with two identical userid. Run localhost/project-g1t8/app/bootstrap, Choose File: student.csv. Import | Show error message "duplicate userid" | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
34 | 2.2 | Validate that in student.csv the e-dollar field must be a numeric value greater or equal to 0.0, and not more than 2 decimal places | userid: amy.ng.2009 password: qwerty128 name: Amy NG school: SIS edollar: -1 userid: ben.ng.2009 password: qwerty129 name: Ben NG school: SIS edollar: 200.999 | Copy the given Test Inputs into student.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: student.csv. Import | Show error message "invalid e-dollar" | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
35 | 2.2 | Validate that the password field in student.csv must not exceed 128 characters. | userid: amy.ng.2009 password: qwerty1281234567890abcdefghijklmnopqrstuvwxyzabcdefghijklmnopqrstuvwxyzabcdefghijklmnopqrstuvwxyzabcdefghijklmnopqrstuvwxyzabcdefghijklmnopqrstuvwxyzabcdefghijklmnopqrstuvwxyzabcdefghijklmnopqrstuvwxyzabcdefghijklmnopqrstuvwxyz name: Amy NG school: SIS edollar: 200 | Copy the given Test Inputs into student.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: student.csv. Import | Show error message "invalid password" | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
36 | 2.2 | Validate that the name field in student.csv must not exceed 100 characters. | userid: amy.ng.2009 password: qwerty128 name: Alpha Beta Gamma Delta Epsilon Zeta Eta Theta Iota Kappa Lambda Mu Nu Xi Omicron Pi Rho Sigma Tau Upsilon Phi Chi Psi Omega NG school: SIS edollar: 200 userid: ben.ng.2009 password: qwerty129 name: Alpha Beta Gamma Delta Epsilon Zeta Eta Theta Iota Kappa Lambda Mu Nu Xi Omicron Pi Rho Sigma Tau Upsilon Phi Chi Psi Omega NG school: SIS edollar: 200 | Copy the given Test Inputs into student.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: student.csv. Import | Show error message "invalid name" | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
37 | 2.2 | Validate that if there are no errors, the data from student.csv in the bootstrap data file is added to the database | userid: calvin.ng.2009 password: qwerty130 name: Calvin NG school: SIS edollar: 200 userid: dawn.ng.2009 password: qwerty131 name: Dawn NG school: SIS edollar: 200 userid: quiten.ng.2009 password: qwerty144 name: Quiten NG school: SOE edollar: 200 userid: ricky.ng.2009 password: qwerty145 name: Ricky NG school: SOE edollar: 200 userid: xavier.ng.2009 password: qwerty151 name: Xavier NG school: SOB edollar: 200 | Copy the given Test Inputs into student.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: student.csv. Import | Bootstrap succeeds. Data successfully added | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
38 | 2.2 | Validate that course.csv has no blank fields: course, school, title, description, exam date, exam start, exam end | course: school: SIS title: All Talk, No Action description: The easiest course of all. We will sit around and talk. exam date: 20131104 exam start: 8:30 exam end: 11:45 course: IS205 school: title: All Talk, No Action description: The easiest course of all. We will sit around and talk. exam date: 20131104 exam start: 8:30 exam end: 11:45 course: IS205 school: SIS title: description: The easiest course of all. We will sit around and talk. exam date: 20131104 exam start: 8:30 exam end: 11:45 course: IS205 school: SIS title: All Talk, No Action description: exam date: 20131104 exam start: 8:30 exam end: 11:45 course: IS205 school: SIS title: All Talk, No Action description: The easiest course of all. We will sit around and talk. exam date: exam start: 8:30 exam end: 11:45 course: IS205 school: SIS title: All Talk, No Action description: The easiest course of all. We will sit around and talk. exam date: 20131104 exam start: exam end: 11:45 course: IS205 school: SIS title: All Talk, No Action description: The easiest course of all. We will sit around and talk. exam date: 20131104 exam start: 8:30 exam end: course: school: title: description: exam date: exam start: exam end: | Copy the given Test Inputs into course.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: course.csv. Import | Show error message "blank [field]" for each blank field, and output in the left-to-right order of the CSV fields | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
39 | 2.2 | Validate that the exam date field in course.csv must be in the format Ymd | course: IS205 school: SIS title: All Talk, No Action description: The easiest course of all. We will sit around and talk. exam date: 11042013 exam start: 8:30 exam end: 11:45 course: IS205 school: SIS title: All Talk, No Action description: The easiest course of all. We will sit around and talk. exam date: 110413 exam start: 8:30 exam end: 11:45 | Copy the given Test Inputs into course.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: course.csv. Import | Show error message "invalid exam date" | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
40 | 2.2 | Validate that the exam start field in course.csv must be in the format H:mm | course: IS205 school: SIS title: All Talk, No Action description: The easiest course of all. We will sit around and talk. exam date: 20131104 exam start: 8:78 exam end: 11:45 course: IS205 school: SIS title: All Talk, No Action description: The easiest course of all. We will sit around and talk. exam date: 20131104 exam start: 0:888 exam end: 11:45 course: IS205 school: SIS title: All Talk, No Action description: The easiest course of all. We will sit around and talk. exam date: 20131104 exam start: 00:15 exam end: 11:45 | Copy the given Test Inputs into course.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: course.csv. Import | Show error message "invalid exam start" | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
41 | 2.2 | Validate that the exam end field in course.csv must be in the format H:mm and the end time should be later than the start time. | course: IS205 school: SIS title: All Talk, No Action description: The easiest course of all. We will sit around and talk. exam date: 20131104 exam start: 13:30 exam end: 11:45 course: IS205 school: SIS title: All Talk, No Action description: The easiest course of all. We will sit around and talk. exam date: 20131104 exam start: 8:30 exam end: 11:4521 course: IS205 school: SIS title: All Talk, No Action description: The easiest course of all. We will sit around and talk. exam date: 20131104 exam start: 8:30 exam end: 121:45 | Copy the given Test Inputs into course.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: course.csv. Import | Show error message "invalid exam end" | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
42 | 2.2 | Validate that the title field in course.csv must not exceed 100 characters. | course: IS205 school: SIS title: All Talk, No Action; This Is THE MOST POPULAR Course in the History of Popular Courses in the Universe description: The easiest course of all. We will sit around and talk. exam date: 20131104 exam start: 8:30 exam end: 11:45 | Copy the given Test Inputs into course.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: course.csv. Import | Show error message "invalid title" | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
43 | 2.2 | Validate that the description field in course.csv must not exceed 1000 characters. | course: IS100 school: SIS title: Calculus description: The basic objective of Calculus is to relate small-scale (differential) quantities to large-scale (integrated) quantities. This is accomplished by means of the Fundamental Theorem of Calculus. Students should demonstrate an understanding of the integral as a cumulative sum, of the derivative as a rate of change, and of the inverse relationship between integration and differentiation. "Calculus, originally called infinitesimal calculus or "the calculus of infinitesimals", is the mathematical study of continuous change, in the same way that geometry is the study of shape and algebra is the study of generalizations of arithmetic operations. It has two major branches, differential calculus and integral calculus. Differential calculus concerns instantaneous rates of change and the slopes of curves. Integral calculus concerns accumulation of quantities and the areas under and between curves. These two branches are related to each other by the fundamental theorem of calculus. Both branches make use of the fundamental notions of convergence of infinite sequences and infinite series to a well-defined limit. Infinitesimal calculus was developed independently in the late 17th century by Isaac Newton and Gottfried Wilhelm Leibniz. Today, calculus has widespread uses in science, engineering, and economics. In mathematics education, calculus denotes courses of elementary mathematical analysis, which are mainly devoted to the study of functions and limits. The word calculus (plural calculi) is a Latin word, meaning originally "small pebble" (this meaning is kept in medicine). Because such pebbles were used for calculation, the meaning of the word has evolved and today usually means a method of computation. It is therefore used for naming specific methods of calculation and related theories, such as propositional calculus, Ricci calculus, calculus of variations, lambda calculus, and process calculus." --from Wikipedia exam date: 20131119 exam start: 8:30 exam end: 11:45 | Copy the given Test Inputs into course.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: course.csv. Import | Show error message "invalid description" | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
44 | 2.2 | Validate that if there are no errors, the data from course.csv in the bootstrap data file is added to the database | course: IS101 school: SIS title: Advanced Calculus description: This is a second course on calculus. It is more advanced definitely. exam date: 20131118 exam start: 12:00 exam end: 15:15 course: IS102 school: SIS title: Java programming description: This course teaches you on Java programming. I love Java definitely. exam date: 20131117 exam start: 15:30 exam end: 18:45 course: IS107 school: SIS title: IT Outsourcing description: This course teaches you on how to outsource your programming projects to others. exam date: 20131112 exam start: 12:00 exam end: 15:15 course: IS200 school: SIS title: Final Touch description: Learn how eat, dress and talk. exam date: 20131109 exam start: 12:00 exam end: 15:15 course: IS205 school: SIS title: All Talk, No Action description: The easiest course of all. We will sit around and talk. exam date: 20131104 exam start: 8:30 exam end: 11:45 | Copy the given Test Inputs into course.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: course.csv. Import | Bootstrap succeeds. Data successfully added | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
45 | 2.2 | Validate that section.csv has no blank fields: course, section, day, start, end, instructor, venue, size | course: section: S1 day: 1 start: 8:30 end: 11:45 instructor: Albert KHOO venue: Seminar Rm 2-1 size: 10 course: IS100 section: day: 1 start: 8:30 end: 11:45 instructor: Albert KHOO venue: Seminar Rm 2-1 size: 10 course: IS100 section: S1 day: start: 8:30 end: 11:45 instructor: Albert KHOO venue: Seminar Rm 2-1 size: 10 course: IS100 section: S1 day: 1 start: end: 11:45 instructor: Albert KHOO venue: Seminar Rm 2-1 size: 10 course: IS100 section: S1 day: 1 start: 8:30 end: instructor: Albert KHOO venue: Seminar Rm 2-1 size: 10 course: IS100 section: S1 day: 1 start: 8:30 end: 11:45 instructor: venue: Seminar Rm 2-1 size: 10 course: IS100 section: S1 day: 1 start: 8:30 end: 11:45 instructor: Albert KHOO venue: size: 10 course: IS100 section: S1 day: 1 start: 8:30 end: 11:45 instructor: Albert KHOO venue: Seminar Rm 2-1 size: course: section: day: start: end: instructor: venue: size: | Copy the given Test Inputs into section.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: section.csv. Import | Show error message "blank [field]" for each blank field, and output in the left-to-right order of the CSV fields | 16/10/2019 Integrity constraint violation: 1062 Duplicate entry 'IS100-S1' for key 'PRIMARY' in D:\mygit\project-g1t8\app\include\SectionDAO.php on line 92 | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
46 | 2.2 | Validate that the course in section.csv must also be found in the course.csv | course: IS400 section: S1 day: 1 start: 8:30 end: 11:45 instructor: Albert KHOO venue: Seminar Rm 2-1 size: 10 | Copy the given Test Inputs into section.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: section.csv. Import | Show error message "invalid course" | 16/10/2019 Integrity constraint violation: 1062 Duplicate entry 'IS100-S1' for key 'PRIMARY' in D:\mygit\project-g1t8\app\include\SectionDAO.php on line 92 | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
47 | 2.2 | Validate that the course in section.csv is a valid course in course.csv and the first character should be an S followed by a positive numeric number (1-99). | course: IS100 section: s1 day: 1 start: 8:30 end: 11:45 instructor: Albert KHOO venue: Seminar Rm 2-1 size: 10 course: IS100 section: S100 day: 1 start: 8:30 end: 11:45 instructor: Albert KHOO venue: Seminar Rm 2-1 size: 10 course: IS100 section: G1 day: 1 start: 8:30 end: 11:45 instructor: Albert KHOO venue: Seminar Rm 2-1 size: 10 course: IS100 section: S0 day: 1 start: 8:30 end: 11:45 instructor: Albert KHOO venue: Seminar Rm 2-1 size: 10 course: IS100 section: 1 day: 1 start: 8:30 end: 11:45 instructor: Albert KHOO venue: Seminar Rm 2-1 size: 10 | Copy the given Test Inputs into section.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: section.csv. Import | Show error message "invalid section" | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
48 | 2.2 | Validate that the day field in section.csv should be a number between 1(inclusive) and 7 (inclusive). 1 - Monday, 2 - Tuesday, ... , 7 - Sunday. | course: IS100 section: S1 day: 0 start: 8:30 end: 11:45 instructor: Albert KHOO venue: Seminar Rm 2-1 size: 10 course: IS100 section: S1 day: 8 start: 8:30 end: 11:45 instructor: Albert KHOO venue: Seminar Rm 2-1 size: 10 course: IS100 section: S1 day: -1 start: 8:30 end: 11:45 instructor: Albert KHOO venue: Seminar Rm 2-1 size: 10 | Copy the given Test Inputs into section.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: section.csv. Import | Show error message "invalid day" | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
49 | 2.2 | Validate that the start field in section.csv must be in the format H:mm (8:30, 12:00, 15:30) | course: IS100 section: S1 day: 1 start: 8:78 end: 11:45 instructor: Albert KHOO venue: Seminar Rm 2-1 size: 10 course: IS100 section: S1 day: 1 start: 8:301 end: 11:45 instructor: Albert KHOO venue: Seminar Rm 2-1 size: 10 course: IS100 section: S1 day: 1 start: 008:30 end: 11:45 instructor: Albert KHOO venue: Seminar Rm 2-1 size: 10 | Copy the given Test Inputs into section.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: section.csv. Import | Show error message "invalid start" | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
50 | 2.2 | Validate that the end field in section.csv must be in the format H:mm and the end time should be later than the start time. (11:45, 15:15, 18:45) | course: IS100 section: S1 day: 1 start: 18:30 end: 11:45 instructor: Albert KHOO venue: Seminar Rm 2-1 size: 10 course: IS100 section: S1 day: 1 start: 8:30 end: 111:45 instructor: Albert KHOO venue: Seminar Rm 2-1 size: 10 course: IS100 section: S1 day: 1 start: 8:30 end: 11:450 instructor: Albert KHOO venue: Seminar Rm 2-1 size: 10 | Copy the given Test Inputs into section.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: section.csv. Import | Show error message "invalid end" | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
51 | 2.2 | Validate that the instructor field in section.csv must not exceed 100 characters. | course: IS100 section: S1 day: 1 start: 8:30 end: 11:45 instructor: Alpha Beta Gamma Delta Epsilon Zeta Eta Theta Iota Kappa Lambda Mu Nu Xi Omicron Pi Rho Sigma Tau Upsilon Phi Chi Psi Omega KHOO venue: Seminar Rm 2-1 size: 10 | Copy the given Test Inputs into section.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: section.csv. Import | Show error message "invalid instructor" | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
52 | 2.2 | Validate that the venue field in section.csv must not exceed 100 characters. | course: IS100 section: S1 day: 1 start: 8:30 end: 11:45 instructor: Albert KHOO venue: Seminar Rm 2000000000000000000000000000000000000000000000000000000-100000000000000000000000000000000000000000000000000001 size: 10 | Copy the given Test Inputs into section.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: section.csv. Import | Show error message "invalid venue" | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
53 | 2.2 | Validate that the size field in section.csv must be a positive numeric number. | course: IS100 section: S1 day: 1 start: 8:30 end: 11:45 instructor: Albert KHOO venue: Seminar Rm 2-1 size: -10 course: IS100 section: S1 day: 1 start: 8:30 end: 11:45 instructor: Albert KHOO venue: Seminar Rm 2-1 size: ten | Copy the given Test Inputs into section.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: section.csv. Import | Show error message "invalid size" | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
54 | 2.2 | Validate that if there are no errors, the data from section.csv in the bootstrap data file is added to the database | course: IS101 section: S1 day: 3 start: 15:30 end: 18:45 instructor: Cheri KHOO venue: Seminar Rm 2-3 size: 10 course: IS101 section: S2 day: 4 start: 8:30 end: 11:45 instructor: Daniel KHOO venue: Seminar Rm 2-4 size: 10 course: IS101 section: S3 day: 5 start: 12:00 end: 15:15 instructor: Ernest KHOO venue: Seminar Rm 2-5 size: 10 course: IS107 section: S1 day: 3 start: 15:30 end: 18:45 instructor: Ray KHOO venue: Seminar Rm 2-18 size: 10 course: IS107 section: S2 day: 4 start: 8:30 end: 11:45 instructor: Simon KHOO venue: Seminar Rm 2-19 size: 10 | Copy the given Test Inputs into section.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: section.csv. Import | Bootstrap succeeds. Data successfully added | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
55 | 2.2 | Validate that prerequisite.csv has no blank fields: course, prerequisite | course: prerequisite: IS100 course: IS101 prerequisite: course: prerequisite: | Copy the given Test Inputs into prerequisite.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: prerequisite.csv. Import | Show error message "blank [field]" for each blank field, and output in the left-to-right order of the CSV fields | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
56 | 2.2 | Validate that the course code of 'course' in prerequisite.csv must also be found in the course.csv | course: IS401 prerequisite: IS100 course: SIS101 prerequisite: IS100 course: IS1011 prerequisite: IS100 | Copy the given Test Inputs into prerequisite.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: prerequisite.csv. Import | Show error message "invalid course" | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
57 | 2.2 | Validate that the course code of 'prerequisite' in prerequisite.csv must also be found in the course.csv | course: IS101 prerequisite: IS1000 course: IS101 prerequisite: IS598 course: IS204 prerequisite: IS88 | Copy the given Test Inputs into prerequisite.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: prerequisite.csv. Import | Show error message "invalid prerequisite" | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
58 | 2.2 | Validate that if there are no errors, the data from prerequisite.csv in the bootstrap data file is added to the database | course: IS101 prerequisite: IS100 course: IS103 prerequisite: IS102 course: IS203 prerequisite: IS106 | Copy the given Test Inputs into prerequisite.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: prerequisite.csv. Import | Bootstrap succeeds. Data successfully added | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
59 | 2.2 | Validate that course_completed.csv has no blank fields: userid, code | userid: code: IS102 userid: ben.ng.2009 code: userid: code: | Copy the given Test Inputs into course_completed.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: course_completed.csv. Import | Show error message "blank [field]" for each blank field, and output in the left-to-right order of the CSV fields | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
60 | 2.2 | Validate that the userid in course_completed.csv is found in student.csv. | userid: rickety.ng.2009 code: IS106 userid: garrulous.ng.2009 code: IS102 | Copy the given Test Inputs into course_completed.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: course_completed.csv. Import | Show error message "invalid userid" | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
61 | 2.2 | Validate that the course code in course_completed.csv is found in the course.csv. | userid: ben.ng.2009 code: IS500 userid: gary.ng.2009 code: MGMT1000 | Copy the given Test Inputs into course_completed.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: course_completed.csv. Import | Show error message "invalid course" | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
62 | 2.2 | Validate that errors are reported if the pre-requisite course has yet to be attempted | userid: amy.ng.2009 code: IS102 userid: gary.ng.2009 code: IS103 | Copy the given Test Inputs into course_completed.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: course_completed.csv. Import | Show error message "invalid course completed" | 16/10/2019 No error displayed, bootstrap has been successful | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
63 | 2.2 | Validate that if there are no errors, the data from course_completed.csv in the bootstrap data file is added to the database | userid: amy.ng.2009 code: IS100 userid: gary.ng.2009 code: IS100 | Copy the given Test Inputs into course_completed.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: course_completed.csv. Import | Bootstrap succeeds. Data successfully added | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
64 | 2.2 | Validate that bid.csv has no blank fields: userid, amount, code, section, status | userid: amount: 33 code: MGMT001 section: S1 status: Pending userid: zac.ng.2009 amount: code: MGMT001 section: S1 status: Pending userid: zac.ng.2009 amount: 33 code: section: S1 status: Pending userid: zac.ng.2009 amount: 33 code: MGMT001 section: status: Pending userid: zac.ng.2009 amount: 33 code: MGMT001 section: S1 status: userid: amount: code: section: status: | Copy the given Test Inputs into bid.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: bid.csv. Import | Show error message "blank [field]" for each blank field, and output in the left-to-right order of the CSV fields | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
65 | 2.2 | Validate that the userid in bid.csv is found in student.csv. | userid: rickety.ng.2009 amount: 33 code: IS100 section: S1 status: Pending userid: garrulous.ng.2009 amount: 20 code: IS100 section: S1 status: Pending | Copy the given Test Inputs into bid.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: bid.csv. Import | Show error message "invalid userid" | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
66 | 2.2 | Validate that the amount in bid.csv must be a positive number >= e$10.00 and not more than 2 decimal places. | userid: zac.ng.2009 amount: 7.89 code: MGMT001 section: S1 status: Pending userid: zac.ng.2009 amount: 12.001 code: MGMT001 section: S1 status: Pending userid: zac.ng.2009 amount: 1.1 code: MGMT001 section: S1 status: Pending | Copy the given Test Inputs into bid.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: bid.csv. Import | Show error message "invalid amount" | 16/10/2019 No error displayed for row 9 & 11 userid: zac.ng.2009 amount: 7.89 code: MGMT001 section: S1 status: Pending bootstrap successful userid: zac.ng.2009 amount: 1.1 code: MGMT001 section: S1 status: Pending This has entered the database | 17/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
67 | 2.2 | Validate that the course code in bid.csv is found in the course.csv. | userid: zac.ng.2009 amount: 10 code: IS401 section: S1 status: Pending userid: zac.ng.2009 amount: 12.01 code: IS1000 section: S1 status: Pending userid: zac.ng.2009 amount: 24 code: IS987 section: S1 status: Pending | Copy the given Test Inputs into bid.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: bid.csv. Import | Show error message "invalid course" | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
68 | 2.2 | Validate that the course code in bid.csv is found in the course.csv and the section code in bid.csv is found in the section.csv. | userid: olivia.ng.2009 amount: 11 code: IS100 section: S3 status: Pending userid: kelly.ng.2009 amount: 22 code: IS103 section: S4 status: Pending userid: ian.ng.2009 amount: 33 code: IS100 section: G1 status: Pending | Copy the given Test Inputs into bid.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: bid.csv. Import | Show error message "invalid section" | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
69 | 2.2 | Validate that in bidding round 1, student is unable to place bids where course is not offered by the student's school | Bidding round 1: open userid: zac.ng.2009 amount: 11 code: ECON001 section: S1 status: Pending userid: parker.ng.2009 amount: 22 code: IS103 section: S1 status: Pending userid: ian.ng.2009 amount: 33 code: MGMT002 section: S1 status: Pending | Copy the given Test Inputs into bid.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: bid.csv. Import | Show error message "not own school course" | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
70 | 2.2 | Validate that student is unable to place bids when class timetables clash | userid: kelly.ng.2009 amount: 22 code: IS205 section: S1 status: Pending userid: kelly.ng.2009 amount: 12 code: IS105 section: S1 status: Pending | Copy the given Test Inputs into bid.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: bid.csv. Import | Show error message "class timetable clash" | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
71 | 2.2 | Validate that student is unable to place bids when exam timetables clash | userid: kelly.ng.2009 amount: 22 code: IS205 section: S1 status: Pending userid: kelly.ng.2009 amount: 12 code: IS210 section: S1 status: Pending | Copy the given Test Inputs into bid.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: bid.csv. Import | Show error message "exam timetable clash" | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
72 | 2.2 | Validate that student is unable to place bids for courses where student has not fulfilled the necessary pre-requisite course(s) | userid: amy.ng.2009 amount: 12 code: IS103 section: S1 status: Pending | Copy the given Test Inputs into bid.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: bid.csv. Import | Show error message "incomplete prerequisites" | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
73 | 2.2 | Validate that student is unable to place bids for courses already completed | userid: amy.ng.2009 amount: 12 code: IS100 section: S1 status: Pending | Copy the given Test Inputs into bid.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: bid.csv. Import | Show error message "course completed" | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
74 | 2.2 | Validate that student is unable to place bids for more than 5 sections | userid: ben.ng.2009 amount: 10 code: IS205 section: S1 status: Pending userid: ben.ng.2009 amount: 10 code: IS100 section: S1 status: Pending userid: ben.ng.2009 amount: 10 code: IS105 section: S2 status: Pending userid: ben.ng.2009 amount: 10 code: IS106 section: S2 status: Pending userid: ben.ng.2009 amount: 10 code: IS200 section: S1 status: Pending (the extra 6th bid that should display error message on) userid: ben.ng.2009 amount: 10 code: IS201 section: S1 status: Pending | Copy the given Test Inputs into bid.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: bid.csv. Import | Show error message "section limit reached" for row 32 | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
75 | 2.2 | Validate that student is unable to place bids when there is insufficient e$ | userid: calvin.ng.2009 amount: 198 code: IS205 section: S1 status: Pending userid: calvin.ng.2009 amount: 10 code: IS100 section: S1 status: Pending | Copy the given Test Inputs into bid.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: bid.csv. Import | Show error message "not enough e-dollar" | 16/10/2019 No error displayed, need to edit test inputs under userid: ben.ng.2009 in this row | 17/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
76 | 2.2 | Validate that if there are no errors, the data from bid.csv in the bootstrap data file is added to the database | userid: dawn.ng.2009 amount: 22 code: IS205 section: S1 status: Pending userid: timothy.ng.2009 amount: 12 code: ECON001 section: S1 status: Pending userid: xavier.ng.2009 amount: 43 code: MGMT002 section: S1 status: Pending | Copy the given Test Inputs into bid.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: bid.csv. Import | Bootstrap succeeds. Data successfully added | 16/10/2019 Bootstrap successful except for userid: timothy.ng.2009 amount: 12 code: ECON001 section: S1 status: Pending need to edit bid.csv testcase under userid: timothy.ng.2009 in this row and change from MGMT002 to ECON001 | 17/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
77 | 2.2 | Validate that if the student has two bids for different sections in the same course, their bid and edollar balance are updated | userid: larry.ng.2009 amount: 21 code: IS102 section: S1 userid: larry.ng.2009 amount: 31 code: IS102 section: S2 | Copy the given Test Inputs into bid.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: bid.csv. Import. Check localhost/phpmyadmin to see if the student's bid and edollar are correct. | Bootstrap succeeds. Data successfully added, correct bid and edollar balance shown in database. | 16/10/2019 Edollar balance not updated in database | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
78 | 2.2 | Validate that if the student has two bids for the same section in the same course, their bid and edollar balance are updated | userid: maggie.ng.2009 amount: 10 code: IS102 section: S1 userid: maggie.ng.2009 amount: 20 code: IS102 section: S1 | Copy the given Test Inputs into bid.csv (bootstrap data file). Run localhost/project-g1t8/app/bootstrap, Choose File: bid.csv. Import. Check localhost/phpmyadmin to see if the student's bid and edollar are correct. | Bootstrap succeeds. Data successfully added, correct bid and edollar balance shown in database. | 16/10/2019 Edollar balance not updated in database | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
79 | 2.2 | Validate that during active bidding round, the student is able to drop a bid by specifying the correct course id and section number | Status: opened Userid: ben.ng.2009 Password: qwerty129 Code: IS100 Section: S1 | Student enters course code and section number. Press drop bid button. | drop bid successful | 15/10/2019 Shows error messsage "Cannot access private property Student::$edollar" | 15/10/2019 drop bid successful | 17/10/2019 Iter 2 Regression Testing Matched expected results
80 | 2.3 | Validate that during active bidding round, the student is not able to drop a bid if they key in the one of the following wrongly; course id and section number | Status: opened Userid: calvin.ng.2009 Password: qwerty130 Code: IS101 Section: S1 Code: IS100 Section: S12 | Student enters course code and section number. Press drop bid button. | drop bid unsuccessful, show error message | 15/10/2019 Shows error messsage "Cannot access private property Student::$edollar" | 15/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
81 | 2.3 | Validate that during non-active bidding round, the student is not able to drop a bid by specifying the correct course id and section number | Status: closed Userid: ben.ng.2009 Password: qwerty129 Code: IS100 Section: S1 | Student enters course code and section number. Press drop bid button. | drop bid unsuccessful, show error message | 15/10/2019 Shows error messsage "Cannot access private property Student::$edollar" | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
82 | 2.3 | Validate that during active-bidding round, student is able to drop a bid with correct course id and section number. Then, updated e$ balance is shown to the student | Status: opened Userid: ben.ng.2009 Password: qwerty129 Code: IS100 Section: S1 Existing e$: $x ($200) Amount bidded: $11 Before drop bid: $x After drop bid: $x + $11 | Student enters course code and section number. Press drop bid button. | drop bid successful, with e$ refunded | 15/10/2019 Shows error messsage "Cannot access private property Student::$edollar" | 15/10/2019 drop bid successful but updated e$ not displayed | 15/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
83 | 2.3 | Validate that student is unable to place bids when course code is missing | Status: opened Userid: ben.ng.2009 Password: qwerty129 Code: Section: S1 | Student enters course code and section number. Press drop bid button. | drop bid unsuccessful, show error message | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
84 | 2.3 | Validate that student is unable to place bids when section number is missing | Status: opened Userid: ben.ng.2009 Password: qwerty129 Code: IS100 Section: | Student enters course code and section number. Press drop bid button. | drop bid unsuccessful, show error message | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
85 | 2.3 | Validate that student is unable to place bids when both course code and section number is missing | Status: opened Userid: ben.ng.2009 Password: qwerty129 Code: Section: | Student enters course code and section number. Press drop bid button. | drop bid unsuccessful, show error message | 16/10/2019 Matched expected results | 17/10/2019 Iter 2 Regression Testing Matched expected results
86 | 2.3
87 | 2.3
88