## Slide 1: SPM PM REVIEW
G1T8 - LET'S GIT IT
HILYA SYAZWANI
LIM HUI SIN
LIM JIE MIN
TAN XIN RONG STEFFI
KU SEOUNGLIM (SKY)

## Slide 2
FUNCTIONALITIES
SCHEDULE
  BIRD’S EYE VIEW
  WORK DIVISION
  BUFFER TIME
  CRITICAL PATH ANALYSIS
BUG METRICS
ROLES & RESPONSIBILITIES
  ROLE ALLOCATIONS
  PP AND PM ROTATIONS
RISKS
OVERVIEW

## Slide 3
Do you plan to drop / add any functionalities?
As of now, our team does not plan to drop/add any functionalities.
Do you plan to use any PHP frameworks?
We will not be implementing any PHP frameworks.
Did you manage to finish login + 1 functionality?
We managed to finish the login page (1.1), and nearly completed the bidding results table (1.5) and bootstrap (2.2), both of which will be pushed to Iter 2.
This occurred as bootstrap took much longer than expected. To mitigate against further scheduling risks, we rescheduled the remaining iterations to include more buffer time.
Cloud deployment details:
  IP Address: http://54.255.141.164/
  Admin Password: g1t8SPMacc@
FUNCTIONALITIES
Notes: Functionalities
Do you plan to drop/add any functionalities?
Do you plan to use any PHP frameworks?
Did you manage to finish login + 1 functionality? (**NEW**)
  What functionalities have you finished? (**NEW**)
  What is the IP address & admin password for your cloud deployment? (**NEW**)

## Slide 4
SCHEDULE
Bird’s eye view
Notes: Schedule
Tell us your schedule. Do not show us the raw schedule on Google Sheets. Summarize it but give us sufficient details to have a bird’s-eye view of your project.
What are your planned iterations and what are the tasks in each iteration?
When is each iteration starting and ending?
Who is doing what?
What are your milestones?
How much buffer time do you have?
Show us your critical path.

## Slide 5
SCHEDULE
Who is doing what? - Task breakdown per member

## Slide 6
SCHEDULE
Who is doing what? - Task breakdown per member

## Slide 7
SCHEDULE
How much buffer time do you have?
For every task on the schedule, there is a buffer time of 1-5 days between tasks, unless the tasks are concurrent.

## Slide 8
CRITICAL PATH ANALYSIS
Iteration 1 - 12 days
1 First meeting and initial planning
3 days
3 Set up database, write code for classes and DAOs
1 day
4 Complete student login
1 day
5 Implement validations for bootstrapping
1 day
6 Implement bidding summary and results table for student
1 day
7 Team meeting, testing and debugging for login
1 day
8 Implement and test admin login
1 day
9 Prepare and submit slides, deploy app
3 days
10 Week 7 PM Review
1 day
2 Daily updates
14 days
Normal task
Critical path
First / last task

## Slide 9
CRITICAL PATH ANALYSIS
Iteration 2 - 6 days (2 paths)
2 Complete and test admin bootstrap
1 day
3 Add necessary methods to classes and DAOs
1 day
4.1 Complete ‘bidding results’, implement and test ‘add bid’ functionality
1 day
5 Implement and test ‘open/close round’ functionality
1 day
6 Iter2 regression testing and debugging
1 day
7 Prepare and submit slides
1 day
8 Deploy app
1 day
4.3 Implement and test ‘drop section’ functionality
1 day
4.2 Implement and test ‘drop bid’ functionality
1 day
9 Week 9 Application Demo and Progress Update Presentation
1 day
1 Daily updates
14 days

## Slide 10
CRITICAL PATH ANALYSIS
Iteration 3 - 5 days (2 paths)
2 Implement and test bidding clearing logic
1 day
3.1 Write test cases for JSON API
1 day
4 Iter3 testing and debugging
1 day
5 App deployment
1 day
6 Week 11 User Acceptance Test
1 day
3.2 Complete JSON API functionalities up to ‘stop round’
1 day
3.3 Finish the remaining JSON API functionalities
1 day
1 Daily updates
14 days

## Slide 11
CRITICAL PATH ANALYSIS
Iteration 4 - 4 days
2 Team meeting and plan (with UAT feedback)
1 day
3 Programming / app debugging (Part 1)
1 day
4 Programming / app debugging (Part 2)
1 day
5 Iter4 testing and debugging
1 day
1 Daily updates
14 days

## Slide 12
CRITICAL PATH ANALYSIS
Iteration 5 - 4 days
2 Prepare slides for Week 14 submission
2 days
3 Check and submit all project files in repository
1 day
4 Final app deployment
2 days
5 Week 14 Final Presentation
1 day
1 Daily updates
3 days

## Slide 13
BUG METRICS
All bugs were found during the scheduled testing and debugging sessions for each functionality. All bugs were hence debugged and resolved immediately, without needing to reschedule.
Notes: Bug Metrics
What is the current value for the metric & did you have to take any action according to your mitigation plan?

## Slide 14
Iteration 1
  PM: Steffi - Milestone: Week 7 PM Review
  Coder: Hui Sin, Jie Min, Hilya, Sky
Iteration 2
  PM: Hui Sin - Milestone: Week 9 Application Demo and Progress Update
  Coder: Steffi, Jie Min, Hilya, Sky
Iteration 3
  PM: Hilya - Milestone: Week 11 User Acceptance Test
  Coder: Steffi, Hui Sin, Jie Min, Sky
Iteration 4
  PM: Jie Min - Milestone: Completion of BIOS
  Coder: Steffi, Hui Sin, Hilya, Sky
Iteration 5
  PM: Sky - Milestone: Week 14 Project Submission and Final Presentation
  Coder: Steffi, Hui Sin, Jie Min, Hilya
ROLES & RESPONSIBILITIES
Role allocations for each iteration
Notes: Roles & responsibilities
Who is doing what (Project Manager, coder, etc.)?
What is the rotation plan? List specifically the PM is in charge of which milestone?

## Slide 15
ROLES AND RESPONSIBILITIES
Pair programming and PM rotations
Notes: What are the pair programming teams and the rotation plan for the teams?